## Setup
Name | Consumer Electronic
Start | 2024-09-27
Periods | Quarter
Cost Modeling | Off
Display hash | Off
Copyright 2024 Paul Galjan
Workstreams |  |  | Phases | [5 empty] | A07B95BB
Order | Worksheet | Workstream | Include | Phase | Periods | Multiplier | Start | End | hash
1 | Hardware | Hardware | Yes | Phase 1 | 2 | 0% | 2024-09-27 | 2025-03-27 | 486504EE
2 | Software | Software | Yes | Phase 2 | 4 | 6% | 2025-03-28 | 2026-03-28 | 12A60BB4
3 | template | Foo Workstream |  | Phase 3 | 8 | 20% | 2026-03-29 | 2028-03-29 | 8D373C1C
4 |  |  |  | Phase 4 | 8 | -5% | 2028-03-30 | 2030-03-30 | C7E832FB
5 |  |  |  | Phase 5 | 2 |  | 2030-03-31 | 2030-09-30 | 37D13D58
6 |  |  |  | Phase 6 | 2 |  | 2030-10-01 | 2031-04-01 | 572A2A2
7 |  |  |  | Phase 7 | 2 |  | 2031-04-02 | 2031-10-02 | ABFCC291
8 |  |  |  | Phase 8 | 2 |  | 2031-10-03 | 2032-04-03 | C69C8F55
9 |  |  |  | Phase 9 | 2 |  | 2032-04-04 | 2032-10-04 | DFB38E3A
10 |  |  |  | Phase 10 | 2 |  | 2032-10-05 | 2033-04-05 | 1CCF9FD1
11 |  |  |  | Phase 11 | 2 |  | 2033-04-06 | 2033-10-06 | 6CAAAD73
12 |  |  |  | Phase 12 | 2 |  | 2033-10-07 | 2034-04-07 | A3F28023
Formulas:
Start = IF(OR([Phase]="",J10=""),"",IF([Start, row above]="Start",Setup!$C4,[End, row above]+1))
End = IF(OR([Phase]="",K10=""),"",EDATE([Start],([Periods]*(SWITCH(Setup!C$5,"Year",12,"Quarter",3,"Month",1,"Week",0.25,"Day",12/30)))))
Structure Planner
Permission is hereby granted, free of charge, to any person obtaining a copy of this software and associated documentation files (the “Software”), to deal in the Software without restriction, including without limitation the rights to use, copy, modify, merge, publish, distribute, sublicense, and/or sell copies of the Software, and to permit persons to whom the Software is furnished to do so, subject to the following conditions:
The above copyright notice and this permission notice shall be included in all copies or substantial portions of the Software.
THE SOFTWARE IS PROVIDED “AS IS”, WITHOUT WARRANTY OF
ANY KIND, EXPRESS OR IMPLIED, INCLUDING BUT NOT LIMITED TO THE WARRANTIES OF MERCHANTABILITY, FITNESS FOR A PARTICULAR PURPOSE AND NONINFRINGEMENT. IN NO EVENT SHALL THE AUTHORS OR COPYRIGHT HOLDERS BE LIABLE FOR ANY CLAIM, DAMAGES OR OTHER LIABILITY, WHETHER IN AN ACTION OF CONTRACT, TORT OR OTHERWISE, ARISING FROM, OUT OF OR IN CONNECTION WITH THE SOFTWARE OR THE USE OR OTHER DEALINGS IN THE SOFTWARE.

## Dashboard
Hardware | Software | template
Hardware | Software | Foo Workstream
Measures | Measures | Measures
6 | 6 | 4
21 | 17 | 11
19 | 9 | 6
14.7 fte | 8.0 fte | 5.3 fte
Tasks | Tasks | Tasks
• Ideation 4 subtasks, 4 resources, 1.3 fte | • Ideation 4 subtasks, 3 resources, 1.3 fte | • Ideation 4 subtasks, 3 resources, 1.3 fte
• Design 9 subtasks, 8 resources, 3.1 fte | • Design 3 subtasks, 2 resources, 2.3 fte | • Design 3 subtasks, 2 resources, 2.3 fte
• Prototype 3 subtasks, 3 resources, 1.8 fte | • Prototype 2 subtasks, 2 resources, 0.5 fte | • Prototype 2 subtasks, 2 resources, 0.5 fte
• Development 4 subtasks, 4 resources, 2.9 fte | • Development 3 subtasks, 1 resources, 0.3 fte | • Development 2 subtasks, 1 resources, 0.2 fte
• Testing 5 subtasks, 3 resources, 1.8 fte | • Testing 3 subtasks, 3 resources, 1.2 fte
• Operations 4 subtasks, 4 resources, 2.9 fte | • Operations 2 subtasks, 2 resources, 1.4 fte
Structure Planner

## Hardware
[6 empty] | pillar | phase | defined | expType | resType | Task | Subtask | Resource | Phase 1 | Phase 2 | 1 | Design | Assembly | Analyst
Workstream | Hardware |  |  |  |  | Hardware | 0 | TRUE | Opex | fte | Ideation | Product Experience | Product Manager | 0.75 | 0.75 |  | Development | CAD | CAD Designer
[6 empty] | Hardware | 0 | TRUE | Opex | fte | Ideation | Feasibility | Marketer | 0.3 | 0.3 |  | Ideation | CNC/3d print | Contract Analyst
display | Task | subtasks | resources | fte | cost | Hardware | 0 | TRUE | Opex | fte | Ideation | Finance Support | Finance Analyst | 0.2 | 0.2 |  | Operations | Day 0 / Packaging | Director
• Ideation 4 subtasks, 4 resources, 1.3 fte | Ideation | 4 | 4 | 1.25 |  | Hardware | 0 | TRUE | Opex | fte | Ideation | Market Research | Market Analyst | 0.3 | 0.3 |  | Prototype | Day 1 | Equipment Leasing
• Design 9 subtasks, 8 resources, 3.1 fte | Design | 9 | 8 | 3.1 |  | Hardware | 0 | TRUE | Opex | fte | Design | Day -1 | Offer Analyst | 0.1 | 0.1 |  | Testing | Day -1 | Equipment Procurement
• Prototype 3 subtasks, 3 resources, 1.8 fte | Prototype | 3 | 3 | 1.8 |  | Hardware | 0 | TRUE | Opex | fte | Design | Day 0 / Packaging | Logistics Analyst | 0.2 | 0.2 |  |  | Day 2 | Facilities Maintenance
• Development 4 subtasks, 4 resources, 2.9 fte | Development | 4 | 4 | 2.9 |  | Hardware | 0 | TRUE | Opex | fte | Design | Day 1 | Software Engineer 2 | 2 | 2 |  |  | Design Review | Finance Analyst
• Testing 5 subtasks, 3 resources, 1.8 fte | Testing | 5 | 3 | 1.8 |  | Hardware | 0 | TRUE | Opex | fte | Design | Day 1 | UX Designer | 0.5 | 0.5 |  |  | Durability/Stress | General Capex
• Operations 4 subtasks, 4 resources, 2.9 fte | Operations | 4 | 4 | 2.9 |  | Hardware | 0 | FALSE |  |  | Design | Day 2 | undefined resource | 0.5 | 0.5 |  |  | Factory Flow | General Opex
[6 empty] | Hardware | 0 | TRUE | Opex | fte | Design | CAD | CAD Designer | 0.2 | 0.2 |  |  | Feasibility | Hardware Engineer 1
[6 empty] | Hardware | 0 | TRUE | Opex | fte | Design | Day 2 | UX Designer | 0.2 | 0.2 |  |  | Finance Support | Hardware Engineer 2
[6 empty] | Hardware | 0 | TRUE | Opex | fte | Design | Design Review | Hardware Engineer 3 | 0.1 | 0.1 |  |  | Integration Testing | Hardware Engineer 3
[6 empty] | Hardware | 0 | TRUE | Opex | fte | Design | Serviceability Review | Support Engineer 2 | 0.3 | 0.3 |  |  | Market Research | Logistics Analyst
[6 empty] | Hardware | 0 | TRUE | Opex | fte | Prototype | CNC/3d print | Machinist 1 | 0.8 | 0.8 |  |  | Pilot Run | Machinist 1
[6 empty] | Hardware | 0 | TRUE | Opex | fte | Prototype | Assembly | Hardware Engineer 2 | 0.1 | 0.1 |  |  | Product Experience | Manager
[6 empty] | Hardware | 0 | TRUE | Opex | fte | Prototype | Durability/Stress | Hardware Engineer 1 | 0.9 | 0.9 |  |  | Program Management | Manager 2
[6 empty] | Hardware | 0 | TRUE | Opex | fte | Development | Factory Flow | Program Manager | 0.5 | 0.5 |  |  | Project Management | Market Analyst
[6 empty] | Hardware | 0 | TRUE | Opex | fte | Development | Project Management | Project Manager | 2 | 2 |  |  | Secret Project | Marketer
[6 empty] | Hardware | 0 | TRUE | Opex | fte | Development | Supply Chain | Logistics Analyst | 0.1 | 0.1 |  |  | Serviceability Review | Offer Analyst
[6 empty] | Hardware | 0 | TRUE | Opex | fte | Development | Supply Chain | Contract Analyst | 0.3 | 0.3 |  |  | Supply Chain | Planner
[6 empty] | Hardware | 0 | TRUE | Opex | fte | Testing | Pilot Run | Hardware Engineer 2 | 0.1 | 0.1 |  |  |  | Product Manager
[6 empty] | Hardware | 0 | TRUE | Opex | fte | Testing | Integration Testing | Software Engineer 2 | 0.5 | 0.5 |  |  |  | Program Manager
[6 empty] | Hardware | 0 | TRUE | Opex | fte | Testing | Integration Testing | Hardware Engineer 2 | 0.5 | 0.5 |  |  |  | Project Manager
[6 empty] | Hardware | 0 | TRUE | Opex | fte | Testing | Pilot Run | Hardware Engineer 1 | 1 | 1 |  |  |  | Software Engineer 1
[6 empty] | Hardware | 0 | TRUE | Opex | fte | Testing | Durability/Stress | Hardware Engineer 1 | 0.2 | 0.2 |  |  |  | Software Engineer 2
[6 empty] | Hardware | 0 | TRUE | Opex | fte | Operations | Program Management | Program Manager | 0.5 | 0.5 |  |  |  | Support Engineer 2
[6 empty] | Hardware | 0 | TRUE | Opex | fte | Operations | Project Management | Project Manager | 2 | 2 |  |  |  | Travel
[6 empty] | Hardware | 0 | FALSE |  |  | Operations | Secret Project | undefined resource | 0.3 | 0.3 |  |  |  | undefined resource
[6 empty] | Hardware | 0 | FALSE |  |  | Operations | Secret Project | undefined resource 2 | 0.1 | 0.1 |  |  |  | undefined resource 2
UX Analyst
UX Designer
Structure Planner
Structure Planner

## Software
[6 empty] | pillar | phase | defined | expType | resType | Task | Subtask | Resource | Phase 1 | Phase 2 | 2 | Design | API contract | Analyst
Workstream | Software |  | Phased | Off |  | Software | Off | TRUE | Opex | fte | Ideation | Product Experience | Product Manager | 0.75 | 0.75 |  | Development | Data model | CAD Designer
[6 empty] | Software | Off | TRUE | Opex | fte | Ideation | Feasibility | Marketer | 0.3 | 0.3 |  | Ideation | Data Model Mockup | Contract Analyst
display | Available Tasks | subtasks | resources | fte | cost | Software | Off | TRUE | Opex | fte | Ideation | Finance Support | Analyst | 0.2 | 0.2 |  | Operations | Feasibility | Director
• Ideation 4 subtasks, 3 resources, 1.3 fte | Ideation | 4 | 3 | 1.25 |  | Software | Off | TRUE | Opex | fte | Ideation | Market Research | Analyst | 0.3 | 0.3 |  | Prototype | Finance Support | Equipment Leasing
• Design 3 subtasks, 2 resources, 2.3 fte | Design | 3 | 2 | 2.3 |  | Software | Off | TRUE | Opex | fte | Design | User journey | UX Designer | 0.1 | 0.1 |  | Testing | Integration Testing | Equipment Procurement
• Prototype 2 subtasks, 2 resources, 0.5 fte | Prototype | 2 | 2 | 0.5 |  | Software | Off | TRUE | Opex | fte | Design | API contract | Software Engineer 2 | 0.2 | 0.2 |  |  | Market Research | Facilities Maintenance
• Development 3 subtasks, 1 resources, 0.3 fte | Development | 3 | 1 | 0.3 |  | Software | Off | TRUE | Opex | fte | Design | Data model | Software Engineer 2 | 2 | 2 |  |  | Operating Environment | Finance Analyst
• Testing 3 subtasks, 3 resources, 1.2 fte | Testing | 3 | 3 | 1.2 |  | Software | Off | TRUE | Opex | fte | Prototype | UI Simulation | UX Designer | 0.5 | 0.5 |  |  | Penetration Testing | General Capex
• Operations 2 subtasks, 2 resources, 1.4 fte | Operations | 2 | 2 | 1.4 |  | Software | Off | TRUE | Opex | fte | Prototype | Data Model Mockup | Software Engineer 2 | 0.5 | 0.5 |  |  | Product Experience | General Opex
[6 empty] | Software | Off | TRUE | Opex | fte | Development | Operating Environment | Software Engineer 1 | 0.2 | 0.2 |  |  | Program Management | Hardware Engineer 1
[6 empty] | Software | Off | TRUE | Opex | fte | Development | Security Hardening | Software Engineer 1 | 0.2 | 0.2 |  |  | Project Management | Hardware Engineer 2
[6 empty] | Software | Off | TRUE | Opex | fte | Development | Unit Testing | Software Engineer 1 | 0.1 | 0.1 |  |  | Security Hardening | Hardware Engineer 3
[6 empty] | Software | Off | TRUE | Opex | fte | Testing | Integration Testing | Software Engineer 2 | 0.3 | 0.3 |  |  | UI Simulation | Logistics Analyst
[6 empty] | Software | Off | TRUE | Opex | fte | Testing | Penetration Testing | Software Engineer 1 | 0.8 | 0.8 |  |  | Unit Testing | Machinist 1
[6 empty] | Software | Off | TRUE | Opex | fte | Testing | UX Workflow Testing | UX Analyst | 0.1 | 0.1 |  |  | User journey | Manager
[6 empty] | Software | Off | TRUE | Opex | fte | Operations | Program Management | Program Manager | 0.9 | 0.9 |  |  | UX Workflow Testing | Manager 2
[6 empty] | Software | Off | TRUE | Opex | fte | Operations | Project Management | Project Manager | 0.5 | 0.5 |  |  |  | Market Analyst
Marketer
Offer Analyst
Planner
Product Manager
Program Manager
Project Manager
Software Engineer 1
Software Engineer 2
Support Engineer 2
Travel
UX Analyst
UX Designer
Structure Planner
Structure Planner
Structure Planner
Structure Planner
Structure Planner
Structure Planner
Structure Planner
Structure Planner
Structure Planner
Structure Planner

## template
[6 empty] | pillar | phase | defined | expType | resType | Task | Subtask | Resource | Phase 1 | Phase 2 | 3 | Design | API contract | Analyst
Workstream | Foo Workstream |  | Phased | Off |  | Foo Workstream | Off | TRUE | Opex | fte | Ideation | Product Experience | Product Manager | 0.75 | 0.75 |  | Development | Data model | CAD Designer
[6 empty] | Foo Workstream | Off | TRUE | Opex | fte | Ideation | Feasibility | Marketer | 0.3 | 0.3 |  | Ideation | Data Model Mockup | Contract Analyst
display | Available Tasks | subtasks | resources | fte | cost | Foo Workstream | Off | TRUE | Opex | fte | Ideation | Finance Support | Analyst | 0.2 | 0.2 |  | Prototype | Feasibility | Director
• Ideation 4 subtasks, 3 resources, 1.3 fte | Ideation | 4 | 3 | 1.25 |  | Foo Workstream | Off | TRUE | Opex | fte | Ideation | Market Research | Analyst | 0.3 | 0.3 |  |  | Finance Support | Equipment Leasing
• Design 3 subtasks, 2 resources, 2.3 fte | Design | 3 | 2 | 2.3 |  | Foo Workstream | Off | TRUE | Opex | fte | Design | User journey | UX Designer | 0.1 | 0.1 |  |  | Market Research | Equipment Procurement
• Prototype 2 subtasks, 2 resources, 0.5 fte | Prototype | 2 | 2 | 0.5 |  | Foo Workstream | Off | TRUE | Opex | fte | Design | API contract | Software Engineer 2 | 0.2 | 0.2 |  |  | Operating Environment | Facilities Maintenance
• Development 2 subtasks, 1 resources, 0.2 fte | Development | 2 | 1 | 0.2 |  | Foo Workstream | Off | TRUE | Opex | fte | Design | Data model | Software Engineer 2 | 2 | 2 |  |  | Product Experience | Finance Analyst
[6 empty] | Foo Workstream | Off | TRUE | Opex | fte | Prototype | UI Simulation | UX Designer | 0.5 | 0.5 |  |  | Security Hardening | General Capex
[6 empty] | Foo Workstream | Off | TRUE | Opex | fte | Prototype | Data Model Mockup | Software Engineer 2 | 0.5 | 0.5 |  |  | UI Simulation | General Opex
[6 empty] | Foo Workstream | Off | TRUE | Opex | fte | Development | Operating Environment | Software Engineer 1 | 0.2 | 0.2 |  |  | User journey | Hardware Engineer 1
[6 empty] | Foo Workstream | Off | TRUE | Opex | fte | Development | Security Hardening | Software Engineer 1 | 0.2 | 0.2 |  |  |  | Hardware Engineer 2
Hardware Engineer 3
Logistics Analyst
Machinist 1
Manager
Manager 2
Market Analyst
Marketer
Offer Analyst
Planner
Product Manager
Program Manager
Project Manager
Software Engineer 1
Software Engineer 2
Support Engineer 2
Travel
UX Analyst
UX Designer
Structure Planner
Structure Planner
Structure Planner
Structure Planner
Structure Planner
Structure Planner
Structure Planner
Structure Planner
Structure Planner
Structure Planner
Structure Planner
Structure Planner
Structure Planner
Structure Planner
Structure Planner
Structure Planner

## Resources
Turn on Cost Modeling in the Workstreams sheet to enable resource definition | [5 empty] | A32204BB
expendType | resourceType | Resource | YearlyMin | YearlyMax | estPerUnit | hash
Opex | fte | Product Manager | 130000 | 170000 | 1 | CA0C0CBA
Opex | fte | Marketer | 80000 | 120000 | 1 | D613B165
Opex | fte | Finance Analyst | 70000 | 100000 | 1 | AE3742C6
Opex | fte | Market Analyst | 70000 | 100000 | 1 | AB318C92
Opex | fte | Offer Analyst | 70000 | 90000 | 1 | 3E839D96
Opex | fte | Logistics Analyst | 60000 | 90000 | 1 | 1BFAE299
Opex | fte | Software Engineer 2 | 110000 | 150000 | 1 | 3801CA76
Opex | fte | UX Designer | 90000 | 130000 | 1 | 765B2774
Opex | fte | Hardware Engineer 3 | 130000 | 160000 | 1 | F53D35E2
Opex | fte | Support Engineer 2 | 70000 | 100000 | 1 | 37C5058E
Opex | fte | Machinist 1 | 45000 | 65000 | 1 | 2A7BE755
Opex | fte | Hardware Engineer 2 | 100000 | 130000 | 1 | 8E02F3D7
Opex | fte | Hardware Engineer 1 | 80000 | 110000 | 1 | 6E1C46D4
Opex | fte | Program Manager | 120000 | 160000 | 1 | BA350247
Opex | fte | Project Manager | 90000 | 130000 | 1 | 9F3DE8AC
Opex | fte | Contract Analyst | 70000 | 100000 | 1 | 71F37300
Opex | fte | Software Engineer 1 | 90000 | 120000 | 1 | 13970C95
Opex | fte | Planner | 60000 | 90000 | 1 | CEB179E2
Opex | fte | Analyst | 60000 | 90000 | 1 | EEBC0BC
Opex | fte | UX Analyst | 80000 | 110000 | 1 | 80C6771
Opex | fte | Manager | 90000 | 130000 | 1 | 3DEF0843
Opex | fte | Manager 2 | 110000 | 160000 | 1 | D23240FD
Opex | fte | Director | 150000 | 250000 | 1 | C2171DAC
Opex | fte | CAD Designer | 80000 | 120000 | 1 | FF0A5F8B
Capex | misc | General Capex |  |  | 1 | E82E109D
Opex | misc | General Opex |  |  | 1 | 1D6BBC7A
Opex | services | Travel |  |  | 1 | A5398404
Opex | services | Facilities Maintenance |  |  | 1 | 373EDCFA
Capex | capital equipment | Equipment Procurement |  |  | 1 | BCA18F70
Opex | services | Equipment Leasing |  |  | 1 | BC8D4935
Structure Planner

## enum (hidden)
Hardware | pillar | phase | defined | expType | resType | Task | Subtask | Resource | Phase 1 | Phase 2 | 0 | 0 | 0 | BaseCost | Phase 1 | Phase 2 | Phase 3 | Phase 4 | Phase 5 | Phase 6 | Phase 7 | Phase 8 | Phase 9 | Phase 10 | Phase 11 | Phase 12
Software | Hardware | 0 | TRUE | Opex | fte | Ideation | Product Experience | Product Manager | 0.75 | 0.75 |  |  |  | 0.75 | 0.75
template | Hardware | 0 | TRUE | Opex | fte | Ideation | Feasibility | Marketer | 0.3 | 0.3 |  |  |  | 0.3 | 0.3
0 | Hardware | 0 | TRUE | Opex | fte | Ideation | Finance Support | Finance Analyst | 0.2 | 0.2 |  |  |  | 0.2 | 0.2
0 | Hardware | 0 | TRUE | Opex | fte | Ideation | Market Research | Market Analyst | 0.3 | 0.3 |  |  |  | 0.3 | 0.3
0 | Hardware | 0 | TRUE | Opex | fte | Design | Day -1 | Offer Analyst | 0.1 | 0.1 |  |  |  | 0.1 | 0.1
0 | Hardware | 0 | TRUE | Opex | fte | Design | Day 0 / Packaging | Logistics Analyst | 0.2 | 0.2 |  |  |  | 0.2 | 0.2
0 | Hardware | 0 | TRUE | Opex | fte | Design | Day 1 | Software Engineer 2 | 2 | 2 |  |  |  | 2 | 2
0 | Hardware | 0 | TRUE | Opex | fte | Design | Day 1 | UX Designer | 0.5 | 0.5 |  |  |  | 0.5 | 0.5
0 | Hardware | 0 | FALSE |  |  | Design | Day 2 | undefined resource | 0.5 | 0.5
0 | Hardware | 0 | TRUE | Opex | fte | Design | CAD | CAD Designer | 0.2 | 0.2 |  |  |  | 0.2 | 0.2
0 | Hardware | 0 | TRUE | Opex | fte | Design | Day 2 | UX Designer | 0.2 | 0.2 |  |  |  | 0.2 | 0.2
| Hardware | 0 | TRUE | Opex | fte | Design | Design Review | Hardware Engineer 3 | 0.1 | 0.1 |  |  |  | 0.1 | 0.1
| Hardware | 0 | TRUE | Opex | fte | Design | Serviceability Review | Support Engineer 2 | 0.3 | 0.3 |  |  |  | 0.3 | 0.3
| Hardware | 0 | TRUE | Opex | fte | Prototype | CNC/3d print | Machinist 1 | 0.8 | 0.8 |  |  |  | 0.8 | 0.8
| Hardware | 0 | TRUE | Opex | fte | Prototype | Assembly | Hardware Engineer 2 | 0.1 | 0.1 |  |  |  | 0.1 | 0.1
| Hardware | 0 | TRUE | Opex | fte | Prototype | Durability/Stress | Hardware Engineer 1 | 0.9 | 0.9 |  |  |  | 0.9 | 0.9
| Hardware | 0 | TRUE | Opex | fte | Development | Factory Flow | Program Manager | 0.5 | 0.5 |  |  |  | 0.5 | 0.5
| Hardware | 0 | TRUE | Opex | fte | Development | Project Management | Project Manager | 2 | 2 |  |  |  | 2 | 2
| Hardware | 0 | TRUE | Opex | fte | Development | Supply Chain | Logistics Analyst | 0.1 | 0.1 |  |  |  | 0.1 | 0.1
| Hardware | 0 | TRUE | Opex | fte | Development | Supply Chain | Contract Analyst | 0.3 | 0.3 |  |  |  | 0.3 | 0.3
| Hardware | 0 | TRUE | Opex | fte | Testing | Pilot Run | Hardware Engineer 2 | 0.1 | 0.1 |  |  |  | 0.1 | 0.1
| Hardware | 0 | TRUE | Opex | fte | Testing | Integration Testing | Software Engineer 2 | 0.5 | 0.5 |  |  |  | 0.5 | 0.5
| Hardware | 0 | TRUE | Opex | fte | Testing | Integration Testing | Hardware Engineer 2 | 0.5 | 0.5 |  |  |  | 0.5 | 0.5
| Hardware | 0 | TRUE | Opex | fte | Testing | Pilot Run | Hardware Engineer 1 | 1 | 1 |  |  |  | 1 | 1
| Hardware | 0 | TRUE | Opex | fte | Testing | Durability/Stress | Hardware Engineer 1 | 0.2 | 0.2 |  |  |  | 0.2 | 0.2
| Hardware | 0 | TRUE | Opex | fte | Operations | Program Management | Program Manager | 0.5 | 0.5 |  |  |  | 0.5 | 0.5
| Hardware | 0 | TRUE | Opex | fte | Operations | Project Management | Project Manager | 2 | 2 |  |  |  | 2 | 2
| Hardware | 0 | FALSE |  |  | Operations | Secret Project | undefined resource | 0.3 | 0.3
| Hardware | 0 | FALSE |  |  | Operations | Secret Project | undefined resource 2 | 0.1 | 0.1
| pillar | phase | defined | expType | resType | Task | Subtask | Resource | Phase 1 | Phase 2 | 0 | 0 | 0
| Software | Off | TRUE | Opex | fte | Ideation | Product Experience | Product Manager | 0.75 | 0.75 |  |  |  | 0.75 | 0.75
| Software | Off | TRUE | Opex | fte | Ideation | Feasibility | Marketer | 0.3 | 0.3 |  |  |  | 0.3 | 0.3
| Software | Off | TRUE | Opex | fte | Ideation | Finance Support | Analyst | 0.2 | 0.2 |  |  |  | 0.2 | 0.2
| Software | Off | TRUE | Opex | fte | Ideation | Market Research | Analyst | 0.3 | 0.3 |  |  |  | 0.3 | 0.3
| Software | Off | TRUE | Opex | fte | Design | User journey | UX Designer | 0.1 | 0.1 |  |  |  | 0.1 | 0.1
| Software | Off | TRUE | Opex | fte | Design | API contract | Software Engineer 2 | 0.2 | 0.2 |  |  |  | 0.2 | 0.2
| Software | Off | TRUE | Opex | fte | Design | Data model | Software Engineer 2 | 2 | 2 |  |  |  | 2 | 2
| Software | Off | TRUE | Opex | fte | Prototype | UI Simulation | UX Designer | 0.5 | 0.5 |  |  |  | 0.5 | 0.5
| Software | Off | TRUE | Opex | fte | Prototype | Data Model Mockup | Software Engineer 2 | 0.5 | 0.5 |  |  |  | 0.5 | 0.5
| Software | Off | TRUE | Opex | fte | Development | Operating Environment | Software Engineer 1 | 0.2 | 0.2 |  |  |  | 0.2 | 0.2
| Software | Off | TRUE | Opex | fte | Development | Security Hardening | Software Engineer 1 | 0.2 | 0.2 |  |  |  | 0.2 | 0.2
| Software | Off | TRUE | Opex | fte | Development | Unit Testing | Software Engineer 1 | 0.1 | 0.1 |  |  |  | 0.1 | 0.1
| Software | Off | TRUE | Opex | fte | Testing | Integration Testing | Software Engineer 2 | 0.3 | 0.3 |  |  |  | 0.3 | 0.3
| Software | Off | TRUE | Opex | fte | Testing | Penetration Testing | Software Engineer 1 | 0.8 | 0.8 |  |  |  | 0.8 | 0.8
| Software | Off | TRUE | Opex | fte | Testing | UX Workflow Testing | UX Analyst | 0.1 | 0.1 |  |  |  | 0.1 | 0.1
| Software | Off | TRUE | Opex | fte | Operations | Program Management | Program Manager | 0.9 | 0.9 |  |  |  | 0.9 | 0.9
| Software | Off | TRUE | Opex | fte | Operations | Project Management | Project Manager | 0.5 | 0.5 |  |  |  | 0.5 | 0.5
| pillar | phase | defined | expType | resType | Task | Subtask | Resource | Phase 1 | Phase 2 | 0 | 0 | 0
| Foo Workstream | Off | TRUE | Opex | fte | Ideation | Product Experience | Product Manager | 0.75 | 0.75 |  |  |  | 0.75 | 0.75
| Foo Workstream | Off | TRUE | Opex | fte | Ideation | Feasibility | Marketer | 0.3 | 0.3 |  |  |  | 0.3 | 0.3
| Foo Workstream | Off | TRUE | Opex | fte | Ideation | Finance Support | Analyst | 0.2 | 0.2 |  |  |  | 0.2 | 0.2
| Foo Workstream | Off | TRUE | Opex | fte | Ideation | Market Research | Analyst | 0.3 | 0.3 |  |  |  | 0.3 | 0.3
| Foo Workstream | Off | TRUE | Opex | fte | Design | User journey | UX Designer | 0.1 | 0.1 |  |  |  | 0.1 | 0.1
| Foo Workstream | Off | TRUE | Opex | fte | Design | API contract | Software Engineer 2 | 0.2 | 0.2 |  |  |  | 0.2 | 0.2
| Foo Workstream | Off | TRUE | Opex | fte | Design | Data model | Software Engineer 2 | 2 | 2 |  |  |  | 2 | 2
| Foo Workstream | Off | TRUE | Opex | fte | Prototype | UI Simulation | UX Designer | 0.5 | 0.5 |  |  |  | 0.5 | 0.5
| Foo Workstream | Off | TRUE | Opex | fte | Prototype | Data Model Mockup | Software Engineer 2 | 0.5 | 0.5 |  |  |  | 0.5 | 0.5
| Foo Workstream | Off | TRUE | Opex | fte | Development | Operating Environment | Software Engineer 1 | 0.2 | 0.2 |  |  |  | 0.2 | 0.2
| Foo Workstream | Off | TRUE | Opex | fte | Development | Security Hardening | Software Engineer 1 | 0.2 | 0.2 |  |  |  | 0.2 | 0.2
|  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
|  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
|  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
|  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
|  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
|  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
|  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
|  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
|  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A