## Workstreams
[8 empty] | Populate additional columns to allow summarization by attributes like organization, department, or owner. | #NAME?
Name | Consumer Electronic
Start | 2024-09-26
Periods | Quarter | q
[6 empty] | Hardware | Software
[6 empty] | Hardware | Software
| Phase | Periods | Multiplier | Start | End | Measures | Measures
| Establish | 2 | 0% | 2024-09-26 | 2025-03-26 | 1 | 1
| Evolve | 4 | 6% | 2025-03-27 | 2026-03-27 | 6 | 6
| Grow | 8 | 20% | 2026-03-28 | 2028-03-28 | 21 | 18
| Mature | 8 | -5% | 2028-03-29 | 2030-03-29 | 175015.15 | 2507.95
[6 empty] | 1847000 | 965500
[6 empty] | Tasks | Tasks
[6 empty] | • Ideation 4 subtasks, 4 resources, $185 k | • Ideation 4 subtasks, 3 resources, $180 k
[6 empty] | • Design 9 subtasks, 7 resources, $485 k | • Design 3 subtasks, 2 resources, $297 k
[6 empty] | • Prototype 3 subtasks, 3 resources, $141 k | • Prototype 2 subtasks, 2 resources, $120 k
[6 empty] | • Development 4 subtasks, 4 resources, $323 k | • Development 3 subtasks, 1 resources, $52.5 k
[6 empty] | • Testing 5 subtasks, 3 resources, $248 k | • Testing 3 subtasks, 3 resources, $132.5 k
[6 empty] | • Operations 4 subtasks, 4 resources, $465 k | • Operations 3 subtasks, 3 resources, $183.5 k
Structure Planner

## Resources
Resource | Type | YearlyMin | YearlyMax | estPerUnit | subtask engagements | base qty
Product Manager | Opex | 130000 | 170000 | 150000 | 2 | 1.5
Marketer | Opex | 80000 | 120000 | 100000 | 2 | 0.6
Finance Analyst | Opex | 70000 | 100000 | 85000 | 1 | 0.2
Market Analyst | Opex | 70000 | 100000 | 85000 | 1 | 0.3
Offer Analyst | Opex | 70000 | 90000 | 80000 | 1 | 0.1
Logistics Analyst | Opex | 60000 | 90000 | 75000 | 2 | 0.3
Software Engineer 2 | Opex | 110000 | 150000 | 130000 | 7 | 6
UX Designer | Opex | 90000 | 130000 | 110000 | 4 | 1.3
Hardware Engineer 3 | Opex | 130000 | 160000 | 145000 | 1 | 0.1
Support Engineer 2 | Opex | 70000 | 100000 | 85000 | 1 | 0.3
Machinist 1 | Opex | 45000 | 65000 | 55000 | 1 | 0.8
Hardware Engineer 2 | Opex | 100000 | 130000 | 115000 | 3 | 0.7
Hardware Engineer 1 | Opex | 80000 | 110000 | 95000 | 3 | 2.1
Program Manager | Opex | 120000 | 160000 | 140000 | 3 | 1.9
Project Manager | Opex | 90000 | 130000 | 110000 | 3 | 4.5
Contract Analyst | Opex | 70000 | 100000 | 85000 | 1 | 0.3
Software Engineer 1 | Opex | 90000 | 120000 | 105000 | 4 | 1.3
Planner | Opex | 60000 | 90000 | 75000 | 0 | 0
Analyst | Opex | 60000 | 90000 | 75000 | 2 | 0.5
UX Analyst | Opex | 80000 | 110000 | 95000 | 1 | 0.1
Manager | Opex | 90000 | 130000 | 110000 | 0 | 0
Manager 2 | Opex | 110000 | 160000 | 135000 | 0 | 0
Director | Opex | 150000 | 250000 | 200000 | 0 | 0
CAD Designer | Opex | 80000 | 120000 | 100000 | 1 | 0.2
General Capex | Capex |  |  | 1 | 0 | 0
General Opex | Opex |  |  | 1 | 0 | 0
Travel | Opex |  |  | 1 | 0 | 0
Facilities Maintenance | Opex |  |  | 1 | 0 | 0
Equipment Procurement | Capex |  |  | 1 | 1 | 150000
Equipment Leasing | Opex |  |  | 1 | 2 | 27500
Structure Planner

## Hardware
[5 empty] | pillar | phase | defined | Task | Subtask | Resource | qty |  |  |  |  | Design | Assembly | Analyst
Workstream | Hardware |  | Phased | Off | Hardware | Off | TRUE | Ideation | Product Experience | Product Manager | 0.75 | #N/A | #N/A | #N/A | #N/A | Development | CAD | CAD Designer
[5 empty] | Hardware | Off | TRUE | Ideation | Feasibility | Marketer | 0.3 | #N/A | #N/A | #N/A | #N/A | Ideation | CNC/3d print | Contract Analyst
display | Task | subtasks | resources | qty | Hardware | Off | TRUE | Ideation | Finance Support | Finance Analyst | 0.2 | #N/A | #N/A | #N/A | #N/A | Operations | Day 0 / Packaging | Director
• Ideation 4 subtasks, 4 resources, $185 k | Ideation | 4 | 4 | 185 | Hardware | Off | TRUE | Ideation | Market Research | Market Analyst | 0.3 | #N/A | #N/A | #N/A | #N/A | Prototype | Day 1 | Equipment Leasing
• Design 9 subtasks, 7 resources, $485 k | Design | 9 | 7 | 485 | Hardware | Off | TRUE | Design | Day -1 | Offer Analyst | 0.1 | #N/A | #N/A | #N/A | #N/A | Testing | Day -1 | Equipment Procurement
• Prototype 3 subtasks, 3 resources, $141 k | Prototype | 3 | 3 | 141 | Hardware | Off | TRUE | Design | Day 0 / Packaging | Logistics Analyst | 0.2 | #N/A | #N/A | #N/A | #N/A |  | Day 2 | Facilities Maintenance
• Development 4 subtasks, 4 resources, $323 k | Development | 4 | 4 | 323 | Hardware | Off | TRUE | Design | Day 1 | Software Engineer 2 | 2 | #N/A | #N/A | #N/A | #N/A |  | Design Review | Finance Analyst
• Testing 5 subtasks, 3 resources, $248 k | Testing | 5 | 3 | 248 | Hardware | Off | TRUE | Design | Day 1 | UX Designer | 0.5 | #N/A | #N/A | #N/A | #N/A |  | Durability/Stress | General Capex
• Operations 4 subtasks, 4 resources, $465 k | Operations | 4 | 4 | 465 | Hardware | Off | TRUE | Design | Day 2 | Software Engineer 2 | 0.5 | #N/A | #N/A | #N/A | #N/A |  | Factory Flow | General Opex
[5 empty] | Hardware | Off | TRUE | Design | CAD | CAD Designer | 0.2 | #N/A | #N/A | #N/A | #N/A |  | Feasibility | Hardware Engineer 1
[5 empty] | Hardware | Off | TRUE | Design | Day 2 | UX Designer | 0.2 | #N/A | #N/A | #N/A | #N/A |  | Finance Support | Hardware Engineer 2
[5 empty] | Hardware | Off | TRUE | Design | Design Review | Hardware Engineer 3 | 0.1 | #N/A | #N/A | #N/A | #N/A |  | Integration Testing | Hardware Engineer 3
[5 empty] | Hardware | Off | TRUE | Design | Serviceability Review | Support Engineer 2 | 0.3 | #N/A | #N/A | #N/A | #N/A |  | Lab Equipment | Logistics Analyst
[5 empty] | Hardware | Off | TRUE | Prototype | CNC/3d print | Machinist 1 | 0.8 | #N/A | #N/A | #N/A | #N/A |  | Market Research | Machinist 1
[5 empty] | Hardware | Off | TRUE | Prototype | Assembly | Hardware Engineer 2 | 0.1 | #N/A | #N/A | #N/A | #N/A |  | Pilot Run | Manager
[5 empty] | Hardware | Off | TRUE | Prototype | Durability/Stress | Hardware Engineer 1 | 0.9 | #N/A | #N/A | #N/A | #N/A |  | Product Experience | Manager 2
[5 empty] | Hardware | Off | TRUE | Development | Factory Flow | Program Manager | 0.5 | #N/A | #N/A | #N/A | #N/A |  | Program Management | Market Analyst
[5 empty] | Hardware | Off | TRUE | Development | Project Management | Project Manager | 2 | #N/A | #N/A | #N/A | #N/A |  | Project Management | Marketer
[5 empty] | Hardware | Off | TRUE | Development | Supply Chain | Logistics Analyst | 0.1 | #N/A | #N/A | #N/A | #N/A |  | Serviceability Review | Offer Analyst
[5 empty] | Hardware | Off | TRUE | Development | Supply Chain | Contract Analyst | 0.3 | #N/A | #N/A | #N/A | #N/A |  | Supply Chain | Planner
[5 empty] | Hardware | Off | TRUE | Testing | Pilot Run | Hardware Engineer 2 | 0.1 | #N/A | #N/A | #N/A | #N/A |  |  | Product Manager
[5 empty] | Hardware | Off | TRUE | Testing | Integration Testing | Software Engineer 2 | 0.5 | #N/A | #N/A | #N/A | #N/A |  |  | Program Manager
[5 empty] | Hardware | Off | TRUE | Testing | Integration Testing | Hardware Engineer 2 | 0.5 | #N/A | #N/A | #N/A | #N/A |  |  | Project Manager
[5 empty] | Hardware | Off | TRUE | Testing | Pilot Run | Hardware Engineer 1 | 1 | #N/A | #N/A | #N/A | #N/A |  |  | Software Engineer 1
[5 empty] | Hardware | Off | TRUE | Testing | Durability/Stress | Hardware Engineer 1 | 0.2 | #N/A | #N/A | #N/A | #N/A |  |  | Software Engineer 2
[5 empty] | Hardware | Off | TRUE | Operations | Program Management | Program Manager | 0.5 | #N/A | #N/A | #N/A | #N/A |  |  | Support Engineer 2
[5 empty] | Hardware | Off | TRUE | Operations | Project Management | Project Manager | 2 | #N/A | #N/A | #N/A | #N/A |  |  | Travel
[5 empty] | Hardware | Off | TRUE | Operations | Lab Equipment | Equipment Procurement | 150000 | #N/A | #N/A | #N/A | #N/A |  |  | UX Analyst
[5 empty] | Hardware | Off | TRUE | Operations | Lab Equipment | Equipment Leasing | 25000 | #N/A | #N/A | #N/A | #N/A |  |  | UX Designer
Structure Planner
Structure Planner

## Software
[5 empty] | pillar | phase | defined | Task | Subtask | Resource | qty | Establish | Evolve | Grow | Mature | Design | API contract | Analyst
Workstream | Software |  | Phased | On | Software | On | TRUE | Ideation | Product Experience | Product Manager | 0.75 | 0.75 | 0.795 | 0.9 | 0.7125 | Development | Data model | CAD Designer
[5 empty] | Software | On | TRUE | Ideation | Feasibility | Marketer | 0.3 | 0.3 | 0.318 | 0.36 | 0.285 | Ideation | Data Model Mockup | Contract Analyst
display | Available Tasks | subtasks | resources | cost | Software | On | TRUE | Ideation | Finance Support | Analyst | 0.2 | 0.2 | 0.212 | 0.24 | 0.19 | Operations | Feasibility | Director
• Ideation 4 subtasks, 3 resources, $180 k | Ideation | 4 | 3 | 180 | Software | On | TRUE | Ideation | Market Research | Analyst | 0.3 | 0.3 | 0.318 | 0.36 | 0.285 | Prototype | Finance Support | Equipment Leasing
• Design 3 subtasks, 2 resources, $297 k | Design | 3 | 2 | 297 | Software | On | TRUE | Design | User journey | UX Designer | 0.1 | 0.1 | 0.106 | 0.12 | 0.095 | Testing | Integration Testing | Equipment Procurement
• Prototype 2 subtasks, 2 resources, $120 k | Prototype | 2 | 2 | 120 | Software | On | TRUE | Design | API contract | Software Engineer 2 | 0.2 | 0.2 | 0.212 | 0.24 | 0.19 |  | Market Research | Facilities Maintenance
• Development 3 subtasks, 1 resources, $52.5 k | Development | 3 | 1 | 52.5 | Software | On | TRUE | Design | Data model | Software Engineer 2 | 2 | 2 | 2.12 | 2.4 | 1.9 |  | Office Equipment | Finance Analyst
• Testing 3 subtasks, 3 resources, $132.5 k | Testing | 3 | 3 | 132.5 | Software | On | TRUE | Prototype | UI Simulation | UX Designer | 0.5 | 0.5 | 0.53 | 0.6 | 0.475 |  | Operating Environment | General Capex
• Operations 3 subtasks, 3 resources, $183.5 k | Operations | 3 | 3 | 183.5 | Software | On | TRUE | Prototype | Data Model Mockup | Software Engineer 2 | 0.5 | 0.5 | 0.53 | 0.6 | 0.475 |  | Penetration Testing | General Opex
[5 empty] | Software | On | TRUE | Development | Operating Environment | Software Engineer 1 | 0.2 | 0.2 | 0.212 | 0.24 | 0.19 |  | Product Experience | Hardware Engineer 1
[5 empty] | Software | On | TRUE | Development | Security Hardening | Software Engineer 1 | 0.2 | 0.2 | 0.212 | 0.24 | 0.19 |  | Program Management | Hardware Engineer 2
[5 empty] | Software | On | TRUE | Development | Unit Testing | Software Engineer 1 | 0.1 | 0.1 | 0.106 | 0.12 | 0.095 |  | Project Management | Hardware Engineer 3
[5 empty] | Software | On | TRUE | Testing | Integration Testing | Software Engineer 2 | 0.3 | 0.3 | 0.318 | 0.36 | 0.285 |  | Security Hardening | Logistics Analyst
[5 empty] | Software | On | TRUE | Testing | Penetration Testing | Software Engineer 1 | 0.8 | 0.8 | 0.848 | 0.96 | 0.76 |  | UI Simulation | Machinist 1
[5 empty] | Software | On | TRUE | Testing | UX Workflow Testing | UX Analyst | 0.1 | 0.1 | 0.106 | 0.12 | 0.095 |  | Unit Testing | Manager
[5 empty] | Software | On | TRUE | Operations | Program Management | Program Manager | 0.9 | 0.9 | 0.954 | 1.08 | 0.855 |  | User journey | Manager 2
[5 empty] | Software | On | TRUE | Operations | Project Management | Project Manager | 0.5 | 0.5 | 0.53 | 0.6 | 0.475 |  | UX Workflow Testing | Market Analyst
[5 empty] | Software | On | TRUE | Operations | Office Equipment | Equipment Leasing | 2500 | 2500 | 2650 | 3000 | 2375 |  |  | Marketer
Offer Analyst
Planner
Product Manager
Program Manager
Project Manager
Software Engineer 1
Software Engineer 2
Support Engineer 2
Travel
UX Analyst
UX Designer
Structure Planner
Structure Planner
Structure Planner
Structure Planner
Structure Planner
Structure Planner

## template (hidden)
[5 empty] | pillar | phase | defined | Task | Subtask | Resource | qty | Establish | Evolve | Grow | Mature | Design | API contract | Analyst
Workstream | template |  | Phased | Off | template | Off | TRUE | Ideation | Product Experience | Product Manager | 0.75 | 0.75 | 0.795 | 0.9 | 0.7125 | Development | Data model | CAD Designer
[5 empty] | template | Off | TRUE | Ideation | Feasibility | Marketer | 0.3 | 0.3 | 0.318 | 0.36 | 0.285 | Ideation | Data Model Mockup | Contract Analyst
display | Available Tasks | subtasks | resources | cost | template | Off | TRUE | Ideation | Finance Support | Analyst | 0.2 | 0.2 | 0.212 | 0.24 | 0.19 | Prototype | Feasibility | Director
• Ideation 4 subtasks, 3 resources, $0 k | Ideation | 4 | 3 | 0 | template | Off | TRUE | Ideation | Market Research | Analyst | 0.3 | 0.3 | 0.318 | 0.36 | 0.285 |  | Finance Support | Equipment Leasing
• Design 3 subtasks, 2 resources, $0 k | Design | 3 | 2 | 0 | template | Off | TRUE | Design | User journey | UX Designer | 0.1 | 0.1 | 0.106 | 0.12 | 0.095 |  | Market Research | Equipment Procurement
• Prototype 2 subtasks, 2 resources, $0 k | Prototype | 2 | 2 | 0 | template | Off | TRUE | Design | API contract | Software Engineer 2 | 0.2 | 0.2 | 0.212 | 0.24 | 0.19 |  | Operating Environment | Facilities Maintenance
• Development 2 subtasks, 1 resources, $0 k | Development | 2 | 1 | 0 | template | Off | TRUE | Design | Data model | Software Engineer 2 | 2 | 2 | 2.12 | 2.4 | 1.9 |  | Product Experience | Finance Analyst
[5 empty] | template | Off | TRUE | Prototype | UI Simulation | UX Designer | 0.5 | 0.5 | 0.53 | 0.6 | 0.475 |  | Security Hardening | General Capex
[5 empty] | template | Off | TRUE | Prototype | Data Model Mockup | Software Engineer 2 | 0.5 | 0.5 | 0.53 | 0.6 | 0.475 |  | UI Simulation | General Opex
[5 empty] | template | Off | TRUE | Development | Operating Environment | Software Engineer 1 | 0.2 | 0.2 | 0.212 | 0.24 | 0.19 |  | User journey | Hardware Engineer 1
[5 empty] | template | Off | TRUE | Development | Security Hardening | Software Engineer 1 | 0.2 | 0.2 | 0.212 | 0.24 | 0.19 |  |  | Hardware Engineer 2
Hardware Engineer 3
Logistics Analyst
Machinist 1
Manager
Manager 2
Market Analyst
Marketer
Offer Analyst
Planner
Product Manager
Program Manager
Project Manager
Software Engineer 1
Software Engineer 2
Support Engineer 2
Travel
UX Analyst
UX Designer
Structure Planner
Structure Planner
Structure Planner
Structure Planner
Structure Planner
Structure Planner

## template (2) (hidden)
[5 empty] | pillar | phase | defined | Task | Subtask | Resource | qty | Establish | Evolve | Grow | Mature | Design | API contract | Analyst
Workstream | template |  | Phased | Off | template | Off | TRUE | Ideation | Product Experience | Product Manager | 0.75 | 0.75 | 0.795 | 0.9 | 0.7125 | Development | Data model | CAD Designer
[5 empty] | template | Off | TRUE | Ideation | Feasibility | Marketer | 0.3 | 0.3 | 0.318 | 0.36 | 0.285 | Ideation | Data Model Mockup | Contract Analyst
display | Available Tasks | subtasks | resources | cost | template | Off | TRUE | Ideation | Finance Support | Analyst | 0.2 | 0.2 | 0.212 | 0.24 | 0.19 | Prototype | Feasibility | Director
• Ideation 4 subtasks, 3 resources, $0 k | Ideation | 4 | 3 | 0 | template | Off | TRUE | Ideation | Market Research | Analyst | 0.3 | 0.3 | 0.318 | 0.36 | 0.285 |  | Finance Support | Equipment Leasing
• Design 3 subtasks, 2 resources, $0 k | Design | 3 | 2 | 0 | template | Off | TRUE | Design | User journey | UX Designer | 0.1 | 0.1 | 0.106 | 0.12 | 0.095 |  | Market Research | Equipment Procurement
• Prototype 2 subtasks, 2 resources, $0 k | Prototype | 2 | 2 | 0 | template | Off | TRUE | Design | API contract | Software Engineer 2 | 0.2 | 0.2 | 0.212 | 0.24 | 0.19 |  | Operating Environment | Facilities Maintenance
• Development 2 subtasks, 1 resources, $0 k | Development | 2 | 1 | 0 | template | Off | TRUE | Design | Data model | Software Engineer 2 | 2 | 2 | 2.12 | 2.4 | 1.9 |  | Product Experience | Finance Analyst
[5 empty] | template | Off | TRUE | Prototype | UI Simulation | UX Designer | 0.5 | 0.5 | 0.53 | 0.6 | 0.475 |  | Security Hardening | General Capex
[5 empty] | template | Off | TRUE | Prototype | Data Model Mockup | Software Engineer 2 | 0.5 | 0.5 | 0.53 | 0.6 | 0.475 |  | UI Simulation | General Opex
[5 empty] | template | Off | TRUE | Development | Operating Environment | Software Engineer 1 | 0.2 | 0.2 | 0.212 | 0.24 | 0.19 |  | User journey | Hardware Engineer 1
[5 empty] | template | Off | TRUE | Development | Security Hardening | Software Engineer 1 | 0.2 | 0.2 | 0.212 | 0.24 | 0.19 |  |  | Hardware Engineer 2
Hardware Engineer 3
Logistics Analyst
Machinist 1
Manager
Manager 2
Market Analyst
Marketer
Offer Analyst
Planner
Product Manager
Program Manager
Project Manager
Software Engineer 1
Software Engineer 2
Support Engineer 2
Travel
UX Analyst
UX Designer
Structure Planner
Structure Planner
Structure Planner
Structure Planner
Structure Planner
Structure Planner

## template (3) (hidden)
[5 empty] | pillar | phase | defined | Task | Subtask | Resource | qty | Establish | Evolve | Grow | Mature | Design | API contract | Analyst
Workstream | template |  | Phased | Off | template | Off | TRUE | Ideation | Product Experience | Product Manager | 0.75 | 0.75 | 0.795 | 0.9 | 0.7125 | Development | Data model | CAD Designer
[5 empty] | template | Off | TRUE | Ideation | Feasibility | Marketer | 0.3 | 0.3 | 0.318 | 0.36 | 0.285 | Ideation | Data Model Mockup | Contract Analyst
display | Available Tasks | subtasks | resources | cost | template | Off | TRUE | Ideation | Finance Support | Analyst | 0.2 | 0.2 | 0.212 | 0.24 | 0.19 | Prototype | Feasibility | Director
• Ideation 4 subtasks, 3 resources, $0 k | Ideation | 4 | 3 | 0 | template | Off | TRUE | Ideation | Market Research | Analyst | 0.3 | 0.3 | 0.318 | 0.36 | 0.285 |  | Finance Support | Equipment Leasing
• Design 3 subtasks, 2 resources, $0 k | Design | 3 | 2 | 0 | template | Off | TRUE | Design | User journey | UX Designer | 0.1 | 0.1 | 0.106 | 0.12 | 0.095 |  | Market Research | Equipment Procurement
• Prototype 2 subtasks, 2 resources, $0 k | Prototype | 2 | 2 | 0 | template | Off | TRUE | Design | API contract | Software Engineer 2 | 0.2 | 0.2 | 0.212 | 0.24 | 0.19 |  | Operating Environment | Facilities Maintenance
• Development 2 subtasks, 1 resources, $0 k | Development | 2 | 1 | 0 | template | Off | TRUE | Design | Data model | Software Engineer 2 | 2 | 2 | 2.12 | 2.4 | 1.9 |  | Product Experience | Finance Analyst
[5 empty] | template | Off | TRUE | Prototype | UI Simulation | UX Designer | 0.5 | 0.5 | 0.53 | 0.6 | 0.475 |  | Security Hardening | General Capex
[5 empty] | template | Off | TRUE | Prototype | Data Model Mockup | Software Engineer 2 | 0.5 | 0.5 | 0.53 | 0.6 | 0.475 |  | UI Simulation | General Opex
[5 empty] | template | Off | TRUE | Development | Operating Environment | Software Engineer 1 | 0.2 | 0.2 | 0.212 | 0.24 | 0.19 |  | User journey | Hardware Engineer 1
[5 empty] | template | Off | TRUE | Development | Security Hardening | Software Engineer 1 | 0.2 | 0.2 | 0.212 | 0.24 | 0.19 |  |  | Hardware Engineer 2
Hardware Engineer 3
Logistics Analyst
Machinist 1
Manager
Manager 2
Market Analyst
Marketer
Offer Analyst
Planner
Product Manager
Program Manager
Project Manager
Software Engineer 1
Software Engineer 2
Support Engineer 2
Travel
UX Analyst
UX Designer
Structure Planner
Structure Planner
Structure Planner
Structure Planner
Structure Planner
Structure Planner

## template (4) (hidden)
[5 empty] | pillar | phase | defined | Task | Subtask | Resource | qty | Establish | Evolve | Grow | Mature | Design | API contract | Analyst
Workstream | template |  | Phased | Off | template | Off | TRUE | Ideation | Product Experience | Product Manager | 0.75 | 0.75 | 0.795 | 0.9 | 0.7125 | Development | Data model | CAD Designer
[5 empty] | template | Off | TRUE | Ideation | Feasibility | Marketer | 0.3 | 0.3 | 0.318 | 0.36 | 0.285 | Ideation | Data Model Mockup | Contract Analyst
display | Available Tasks | subtasks | resources | cost | template | Off | TRUE | Ideation | Finance Support | Analyst | 0.2 | 0.2 | 0.212 | 0.24 | 0.19 | Prototype | Feasibility | Director
• Ideation 4 subtasks, 3 resources, $0 k | Ideation | 4 | 3 | 0 | template | Off | TRUE | Ideation | Market Research | Analyst | 0.3 | 0.3 | 0.318 | 0.36 | 0.285 |  | Finance Support | Equipment Leasing
• Design 3 subtasks, 2 resources, $0 k | Design | 3 | 2 | 0 | template | Off | TRUE | Design | User journey | UX Designer | 0.1 | 0.1 | 0.106 | 0.12 | 0.095 |  | Market Research | Equipment Procurement
• Prototype 2 subtasks, 2 resources, $0 k | Prototype | 2 | 2 | 0 | template | Off | TRUE | Design | API contract | Software Engineer 2 | 0.2 | 0.2 | 0.212 | 0.24 | 0.19 |  | Operating Environment | Facilities Maintenance
• Development 2 subtasks, 1 resources, $0 k | Development | 2 | 1 | 0 | template | Off | TRUE | Design | Data model | Software Engineer 2 | 2 | 2 | 2.12 | 2.4 | 1.9 |  | Product Experience | Finance Analyst
[5 empty] | template | Off | TRUE | Prototype | UI Simulation | UX Designer | 0.5 | 0.5 | 0.53 | 0.6 | 0.475 |  | Security Hardening | General Capex
[5 empty] | template | Off | TRUE | Prototype | Data Model Mockup | Software Engineer 2 | 0.5 | 0.5 | 0.53 | 0.6 | 0.475 |  | UI Simulation | General Opex
[5 empty] | template | Off | TRUE | Development | Operating Environment | Software Engineer 1 | 0.2 | 0.2 | 0.212 | 0.24 | 0.19 |  | User journey | Hardware Engineer 1
[5 empty] | template | Off | TRUE | Development | Security Hardening | Software Engineer 1 | 0.2 | 0.2 | 0.212 | 0.24 | 0.19 |  |  | Hardware Engineer 2
Hardware Engineer 3
Logistics Analyst
Machinist 1
Manager
Manager 2
Market Analyst
Marketer
Offer Analyst
Planner
Product Manager
Program Manager
Project Manager
Software Engineer 1
Software Engineer 2
Support Engineer 2
Travel
UX Analyst
UX Designer
Structure Planner
Structure Planner
Structure Planner
Structure Planner
Structure Planner
Structure Planner

## template (5) (hidden)
[5 empty] | pillar | phase | defined | Task | Subtask | Resource | qty | Establish | Evolve | Grow | Mature | Design | API contract | Analyst
Workstream | template |  | Phased | Off | template | Off | TRUE | Ideation | Product Experience | Product Manager | 0.75 | 0.75 | 0.795 | 0.9 | 0.7125 | Development | Data model | CAD Designer
[5 empty] | template | Off | TRUE | Ideation | Feasibility | Marketer | 0.3 | 0.3 | 0.318 | 0.36 | 0.285 | Ideation | Data Model Mockup | Contract Analyst
display | Available Tasks | subtasks | resources | cost | template | Off | TRUE | Ideation | Finance Support | Analyst | 0.2 | 0.2 | 0.212 | 0.24 | 0.19 | Prototype | Feasibility | Director
• Ideation 4 subtasks, 3 resources, $0 k | Ideation | 4 | 3 | 0 | template | Off | TRUE | Ideation | Market Research | Analyst | 0.3 | 0.3 | 0.318 | 0.36 | 0.285 |  | Finance Support | Equipment Leasing
• Design 3 subtasks, 2 resources, $0 k | Design | 3 | 2 | 0 | template | Off | TRUE | Design | User journey | UX Designer | 0.1 | 0.1 | 0.106 | 0.12 | 0.095 |  | Market Research | Equipment Procurement
• Prototype 2 subtasks, 2 resources, $0 k | Prototype | 2 | 2 | 0 | template | Off | TRUE | Design | API contract | Software Engineer 2 | 0.2 | 0.2 | 0.212 | 0.24 | 0.19 |  | Operating Environment | Facilities Maintenance
• Development 2 subtasks, 1 resources, $0 k | Development | 2 | 1 | 0 | template | Off | TRUE | Design | Data model | Software Engineer 2 | 2 | 2 | 2.12 | 2.4 | 1.9 |  | Product Experience | Finance Analyst
[5 empty] | template | Off | TRUE | Prototype | UI Simulation | UX Designer | 0.5 | 0.5 | 0.53 | 0.6 | 0.475 |  | Security Hardening | General Capex
[5 empty] | template | Off | TRUE | Prototype | Data Model Mockup | Software Engineer 2 | 0.5 | 0.5 | 0.53 | 0.6 | 0.475 |  | UI Simulation | General Opex
[5 empty] | template | Off | TRUE | Development | Operating Environment | Software Engineer 1 | 0.2 | 0.2 | 0.212 | 0.24 | 0.19 |  | User journey | Hardware Engineer 1
[5 empty] | template | Off | TRUE | Development | Security Hardening | Software Engineer 1 | 0.2 | 0.2 | 0.212 | 0.24 | 0.19 |  |  | Hardware Engineer 2
Hardware Engineer 3
Logistics Analyst
Machinist 1
Manager
Manager 2
Market Analyst
Marketer
Offer Analyst
Planner
Product Manager
Program Manager
Project Manager
Software Engineer 1
Software Engineer 2
Support Engineer 2
Travel
UX Analyst
UX Designer
Structure Planner
Structure Planner
Structure Planner
Structure Planner
Structure Planner
Structure Planner

## template (6) (hidden)
[5 empty] | pillar | phase | defined | Task | Subtask | Resource | qty | Establish | Evolve | Grow | Mature | Design | API contract | Analyst
Workstream | template |  | Phased | Off | template | Off | TRUE | Ideation | Product Experience | Product Manager | 0.75 | 0.75 | 0.795 | 0.9 | 0.7125 | Development | Data model | CAD Designer
[5 empty] | template | Off | TRUE | Ideation | Feasibility | Marketer | 0.3 | 0.3 | 0.318 | 0.36 | 0.285 | Ideation | Data Model Mockup | Contract Analyst
display | Available Tasks | subtasks | resources | cost | template | Off | TRUE | Ideation | Finance Support | Analyst | 0.2 | 0.2 | 0.212 | 0.24 | 0.19 | Prototype | Feasibility | Director
• Ideation 4 subtasks, 3 resources, $0 k | Ideation | 4 | 3 | 0 | template | Off | TRUE | Ideation | Market Research | Analyst | 0.3 | 0.3 | 0.318 | 0.36 | 0.285 |  | Finance Support | Equipment Leasing
• Design 3 subtasks, 2 resources, $0 k | Design | 3 | 2 | 0 | template | Off | TRUE | Design | User journey | UX Designer | 0.1 | 0.1 | 0.106 | 0.12 | 0.095 |  | Market Research | Equipment Procurement
• Prototype 2 subtasks, 2 resources, $0 k | Prototype | 2 | 2 | 0 | template | Off | TRUE | Design | API contract | Software Engineer 2 | 0.2 | 0.2 | 0.212 | 0.24 | 0.19 |  | Operating Environment | Facilities Maintenance
• Development 2 subtasks, 1 resources, $0 k | Development | 2 | 1 | 0 | template | Off | TRUE | Design | Data model | Software Engineer 2 | 2 | 2 | 2.12 | 2.4 | 1.9 |  | Product Experience | Finance Analyst
[5 empty] | template | Off | TRUE | Prototype | UI Simulation | UX Designer | 0.5 | 0.5 | 0.53 | 0.6 | 0.475 |  | Security Hardening | General Capex
[5 empty] | template | Off | TRUE | Prototype | Data Model Mockup | Software Engineer 2 | 0.5 | 0.5 | 0.53 | 0.6 | 0.475 |  | UI Simulation | General Opex
[5 empty] | template | Off | TRUE | Development | Operating Environment | Software Engineer 1 | 0.2 | 0.2 | 0.212 | 0.24 | 0.19 |  | User journey | Hardware Engineer 1
[5 empty] | template | Off | TRUE | Development | Security Hardening | Software Engineer 1 | 0.2 | 0.2 | 0.212 | 0.24 | 0.19 |  |  | Hardware Engineer 2
Hardware Engineer 3
Logistics Analyst
Machinist 1
Manager
Manager 2
Market Analyst
Marketer
Offer Analyst
Planner
Product Manager
Program Manager
Project Manager
Software Engineer 1
Software Engineer 2
Support Engineer 2
Travel
UX Analyst
UX Designer
Structure Planner
Structure Planner
Structure Planner
Structure Planner
Structure Planner
Structure Planner

## template (7) (hidden)
[5 empty] | pillar | phase | defined | Task | Subtask | Resource | qty | Establish | Evolve | Grow | Mature | Design | API contract | Analyst
Workstream | template |  | Phased | Off | template | Off | TRUE | Ideation | Product Experience | Product Manager | 0.75 | 0.75 | 0.795 | 0.9 | 0.7125 | Development | Data model | CAD Designer
[5 empty] | template | Off | TRUE | Ideation | Feasibility | Marketer | 0.3 | 0.3 | 0.318 | 0.36 | 0.285 | Ideation | Data Model Mockup | Contract Analyst
display | Available Tasks | subtasks | resources | cost | template | Off | TRUE | Ideation | Finance Support | Analyst | 0.2 | 0.2 | 0.212 | 0.24 | 0.19 | Prototype | Feasibility | Director
• Ideation 4 subtasks, 3 resources, $0 k | Ideation | 4 | 3 | 0 | template | Off | TRUE | Ideation | Market Research | Analyst | 0.3 | 0.3 | 0.318 | 0.36 | 0.285 |  | Finance Support | Equipment Leasing
• Design 3 subtasks, 2 resources, $0 k | Design | 3 | 2 | 0 | template | Off | TRUE | Design | User journey | UX Designer | 0.1 | 0.1 | 0.106 | 0.12 | 0.095 |  | Market Research | Equipment Procurement
• Prototype 2 subtasks, 2 resources, $0 k | Prototype | 2 | 2 | 0 | template | Off | TRUE | Design | API contract | Software Engineer 2 | 0.2 | 0.2 | 0.212 | 0.24 | 0.19 |  | Operating Environment | Facilities Maintenance
• Development 2 subtasks, 1 resources, $0 k | Development | 2 | 1 | 0 | template | Off | TRUE | Design | Data model | Software Engineer 2 | 2 | 2 | 2.12 | 2.4 | 1.9 |  | Product Experience | Finance Analyst
[5 empty] | template | Off | TRUE | Prototype | UI Simulation | UX Designer | 0.5 | 0.5 | 0.53 | 0.6 | 0.475 |  | Security Hardening | General Capex
[5 empty] | template | Off | TRUE | Prototype | Data Model Mockup | Software Engineer 2 | 0.5 | 0.5 | 0.53 | 0.6 | 0.475 |  | UI Simulation | General Opex
[5 empty] | template | Off | TRUE | Development | Operating Environment | Software Engineer 1 | 0.2 | 0.2 | 0.212 | 0.24 | 0.19 |  | User journey | Hardware Engineer 1
[5 empty] | template | Off | TRUE | Development | Security Hardening | Software Engineer 1 | 0.2 | 0.2 | 0.212 | 0.24 | 0.19 |  |  | Hardware Engineer 2
Hardware Engineer 3
Logistics Analyst
Machinist 1
Manager
Manager 2
Market Analyst
Marketer
Offer Analyst
Planner
Product Manager
Program Manager
Project Manager
Software Engineer 1
Software Engineer 2
Support Engineer 2
Travel
UX Analyst
UX Designer
Structure Planner
Structure Planner
Structure Planner
Structure Planner
Structure Planner
Structure Planner

## template (8) (hidden)
[5 empty] | pillar | phase | defined | Task | Subtask | Resource | qty | Establish | Evolve | Grow | Mature | Design | API contract | Analyst
Workstream | template |  | Phased | Off | template | Off | TRUE | Ideation | Product Experience | Product Manager | 0.75 | 0.75 | 0.795 | 0.9 | 0.7125 | Development | Data model | CAD Designer
[5 empty] | template | Off | TRUE | Ideation | Feasibility | Marketer | 0.3 | 0.3 | 0.318 | 0.36 | 0.285 | Ideation | Data Model Mockup | Contract Analyst
display | Available Tasks | subtasks | resources | cost | template | Off | TRUE | Ideation | Finance Support | Analyst | 0.2 | 0.2 | 0.212 | 0.24 | 0.19 | Prototype | Feasibility | Director
• Ideation 4 subtasks, 3 resources, $0 k | Ideation | 4 | 3 | 0 | template | Off | TRUE | Ideation | Market Research | Analyst | 0.3 | 0.3 | 0.318 | 0.36 | 0.285 |  | Finance Support | Equipment Leasing
• Design 3 subtasks, 2 resources, $0 k | Design | 3 | 2 | 0 | template | Off | TRUE | Design | User journey | UX Designer | 0.1 | 0.1 | 0.106 | 0.12 | 0.095 |  | Market Research | Equipment Procurement
• Prototype 2 subtasks, 2 resources, $0 k | Prototype | 2 | 2 | 0 | template | Off | TRUE | Design | API contract | Software Engineer 2 | 0.2 | 0.2 | 0.212 | 0.24 | 0.19 |  | Operating Environment | Facilities Maintenance
• Development 2 subtasks, 1 resources, $0 k | Development | 2 | 1 | 0 | template | Off | TRUE | Design | Data model | Software Engineer 2 | 2 | 2 | 2.12 | 2.4 | 1.9 |  | Product Experience | Finance Analyst
[5 empty] | template | Off | TRUE | Prototype | UI Simulation | UX Designer | 0.5 | 0.5 | 0.53 | 0.6 | 0.475 |  | Security Hardening | General Capex
[5 empty] | template | Off | TRUE | Prototype | Data Model Mockup | Software Engineer 2 | 0.5 | 0.5 | 0.53 | 0.6 | 0.475 |  | UI Simulation | General Opex
[5 empty] | template | Off | TRUE | Development | Operating Environment | Software Engineer 1 | 0.2 | 0.2 | 0.212 | 0.24 | 0.19 |  | User journey | Hardware Engineer 1
[5 empty] | template | Off | TRUE | Development | Security Hardening | Software Engineer 1 | 0.2 | 0.2 | 0.212 | 0.24 | 0.19 |  |  | Hardware Engineer 2
Hardware Engineer 3
Logistics Analyst
Machinist 1
Manager
Manager 2
Market Analyst
Marketer
Offer Analyst
Planner
Product Manager
Program Manager
Project Manager
Software Engineer 1
Software Engineer 2
Support Engineer 2
Travel
UX Analyst
UX Designer
Structure Planner
Structure Planner
Structure Planner
Structure Planner
Structure Planner
Structure Planner

## template (9) (hidden)
[5 empty] | pillar | phase | defined | Task | Subtask | Resource | qty | Establish | Evolve | Grow | Mature | Design | API contract | Analyst
Workstream | template |  | Phased | Off | template | Off | TRUE | Ideation | Product Experience | Product Manager | 0.75 | 0.75 | 0.795 | 0.9 | 0.7125 | Development | Data model | CAD Designer
[5 empty] | template | Off | TRUE | Ideation | Feasibility | Marketer | 0.3 | 0.3 | 0.318 | 0.36 | 0.285 | Ideation | Data Model Mockup | Contract Analyst
display | Available Tasks | subtasks | resources | cost | template | Off | TRUE | Ideation | Finance Support | Analyst | 0.2 | 0.2 | 0.212 | 0.24 | 0.19 | Prototype | Feasibility | Director
• Ideation 4 subtasks, 3 resources, $0 k | Ideation | 4 | 3 | 0 | template | Off | TRUE | Ideation | Market Research | Analyst | 0.3 | 0.3 | 0.318 | 0.36 | 0.285 |  | Finance Support | Equipment Leasing
• Design 3 subtasks, 2 resources, $0 k | Design | 3 | 2 | 0 | template | Off | TRUE | Design | User journey | UX Designer | 0.1 | 0.1 | 0.106 | 0.12 | 0.095 |  | Market Research | Equipment Procurement
• Prototype 2 subtasks, 2 resources, $0 k | Prototype | 2 | 2 | 0 | template | Off | TRUE | Design | API contract | Software Engineer 2 | 0.2 | 0.2 | 0.212 | 0.24 | 0.19 |  | Operating Environment | Facilities Maintenance
• Development 2 subtasks, 1 resources, $0 k | Development | 2 | 1 | 0 | template | Off | TRUE | Design | Data model | Software Engineer 2 | 2 | 2 | 2.12 | 2.4 | 1.9 |  | Product Experience | Finance Analyst
[5 empty] | template | Off | TRUE | Prototype | UI Simulation | UX Designer | 0.5 | 0.5 | 0.53 | 0.6 | 0.475 |  | Security Hardening | General Capex
[5 empty] | template | Off | TRUE | Prototype | Data Model Mockup | Software Engineer 2 | 0.5 | 0.5 | 0.53 | 0.6 | 0.475 |  | UI Simulation | General Opex
[5 empty] | template | Off | TRUE | Development | Operating Environment | Software Engineer 1 | 0.2 | 0.2 | 0.212 | 0.24 | 0.19 |  | User journey | Hardware Engineer 1
[5 empty] | template | Off | TRUE | Development | Security Hardening | Software Engineer 1 | 0.2 | 0.2 | 0.212 | 0.24 | 0.19 |  |  | Hardware Engineer 2
Hardware Engineer 3
Logistics Analyst
Machinist 1
Manager
Manager 2
Market Analyst
Marketer
Offer Analyst
Planner
Product Manager
Program Manager
Project Manager
Software Engineer 1
Software Engineer 2
Support Engineer 2
Travel
UX Analyst
UX Designer
Structure Planner
Structure Planner
Structure Planner
Structure Planner
Structure Planner
Structure Planner

## template (10) (hidden)
[5 empty] | pillar | phase | defined | Task | Subtask | Resource | qty | Establish | Evolve | Grow | Mature | Design | API contract | Analyst
Workstream | template |  | Phased | Off | template | Off | TRUE | Ideation | Product Experience | Product Manager | 0.75 | 0.75 | 0.795 | 0.9 | 0.7125 | Development | Data model | CAD Designer
[5 empty] | template | Off | TRUE | Ideation | Feasibility | Marketer | 0.3 | 0.3 | 0.318 | 0.36 | 0.285 | Ideation | Data Model Mockup | Contract Analyst
display | Available Tasks | subtasks | resources | cost | template | Off | TRUE | Ideation | Finance Support | Analyst | 0.2 | 0.2 | 0.212 | 0.24 | 0.19 | Prototype | Feasibility | Director
• Ideation 4 subtasks, 3 resources, $0 k | Ideation | 4 | 3 | 0 | template | Off | TRUE | Ideation | Market Research | Analyst | 0.3 | 0.3 | 0.318 | 0.36 | 0.285 |  | Finance Support | Equipment Leasing
• Design 3 subtasks, 2 resources, $0 k | Design | 3 | 2 | 0 | template | Off | TRUE | Design | User journey | UX Designer | 0.1 | 0.1 | 0.106 | 0.12 | 0.095 |  | Market Research | Equipment Procurement
• Prototype 2 subtasks, 2 resources, $0 k | Prototype | 2 | 2 | 0 | template | Off | TRUE | Design | API contract | Software Engineer 2 | 0.2 | 0.2 | 0.212 | 0.24 | 0.19 |  | Operating Environment | Facilities Maintenance
• Development 2 subtasks, 1 resources, $0 k | Development | 2 | 1 | 0 | template | Off | TRUE | Design | Data model | Software Engineer 2 | 2 | 2 | 2.12 | 2.4 | 1.9 |  | Product Experience | Finance Analyst
[5 empty] | template | Off | TRUE | Prototype | UI Simulation | UX Designer | 0.5 | 0.5 | 0.53 | 0.6 | 0.475 |  | Security Hardening | General Capex
[5 empty] | template | Off | TRUE | Prototype | Data Model Mockup | Software Engineer 2 | 0.5 | 0.5 | 0.53 | 0.6 | 0.475 |  | UI Simulation | General Opex
[5 empty] | template | Off | TRUE | Development | Operating Environment | Software Engineer 1 | 0.2 | 0.2 | 0.212 | 0.24 | 0.19 |  | User journey | Hardware Engineer 1
[5 empty] | template | Off | TRUE | Development | Security Hardening | Software Engineer 1 | 0.2 | 0.2 | 0.212 | 0.24 | 0.19 |  |  | Hardware Engineer 2
Hardware Engineer 3
Logistics Analyst
Machinist 1
Manager
Manager 2
Market Analyst
Marketer
Offer Analyst
Planner
Product Manager
Program Manager
Project Manager
Software Engineer 1
Software Engineer 2
Support Engineer 2
Travel
UX Analyst
UX Designer
Structure Planner
Structure Planner
Structure Planner
Structure Planner
Structure Planner
Structure Planner

## enum
Order | Worksheet | Workstream | Hardware | pillar | phase | defined | Task | Subtask | Resource | qty | 0 | 0 | 0 | BaseCost | Establish | Evolve | Grow | Mature
1 | Hardware | Hardware | Software | Hardware | Off | TRUE | Ideation | Product Experience | Product Manager | 0.75 |  |  |  | 112500 | 112500
2 | Software | Software |  | Hardware | Off | TRUE | Ideation | Feasibility | Marketer | 0.3 |  |  |  | 30000 | 30000
|  |  |  | Hardware | Off | TRUE | Ideation | Finance Support | Finance Analyst | 0.2 |  |  |  | 17000 | 17000
|  |  |  | Hardware | Off | TRUE | Ideation | Market Research | Market Analyst | 0.3 |  |  |  | 25500 | 25500
|  |  |  | Hardware | Off | TRUE | Design | Day -1 | Offer Analyst | 0.1 |  |  |  | 8000 | 8000
|  |  |  | Hardware | Off | TRUE | Design | Day 0 / Packaging | Logistics Analyst | 0.2 |  |  |  | 15000 | 15000
|  |  |  | Hardware | Off | TRUE | Design | Day 1 | Software Engineer 2 | 2 |  |  |  | 260000 | 260000
|  |  |  | Hardware | Off | TRUE | Design | Day 1 | UX Designer | 0.5 |  |  |  | 55000 | 55000
|  |  |  | Hardware | Off | TRUE | Design | Day 2 | Software Engineer 2 | 0.5 |  |  |  | 65000 | 65000
|  |  |  | Hardware | Off | TRUE | Design | CAD | CAD Designer | 0.2 |  |  |  | 20000 | 20000
|  |  |  | Hardware | Off | TRUE | Design | Day 2 | UX Designer | 0.2 |  |  |  | 22000 | 22000
|  |  |  | Hardware | Off | TRUE | Design | Design Review | Hardware Engineer 3 | 0.1 |  |  |  | 14500 | 14500
|  |  |  | Hardware | Off | TRUE | Design | Serviceability Review | Support Engineer 2 | 0.3 |  |  |  | 25500 | 25500
|  |  |  | Hardware | Off | TRUE | Prototype | CNC/3d print | Machinist 1 | 0.8 |  |  |  | 44000 | 44000
|  |  |  | Hardware | Off | TRUE | Prototype | Assembly | Hardware Engineer 2 | 0.1 |  |  |  | 11500 | 11500
|  |  |  | Hardware | Off | TRUE | Prototype | Durability/Stress | Hardware Engineer 1 | 0.9 |  |  |  | 85500 | 85500
|  |  |  | Hardware | Off | TRUE | Development | Factory Flow | Program Manager | 0.5 |  |  |  | 70000 | 70000
|  |  |  | Hardware | Off | TRUE | Development | Project Management | Project Manager | 2 |  |  |  | 220000 | 220000
|  |  |  | Hardware | Off | TRUE | Development | Supply Chain | Logistics Analyst | 0.1 |  |  |  | 7500 | 7500
|  |  |  | Hardware | Off | TRUE | Development | Supply Chain | Contract Analyst | 0.3 |  |  |  | 25500 | 25500
|  |  |  | Hardware | Off | TRUE | Testing | Pilot Run | Hardware Engineer 2 | 0.1 |  |  |  | 11500 | 11500
|  |  |  | Hardware | Off | TRUE | Testing | Integration Testing | Software Engineer 2 | 0.5 |  |  |  | 65000 | 65000
|  |  |  | Hardware | Off | TRUE | Testing | Integration Testing | Hardware Engineer 2 | 0.5 |  |  |  | 57500 | 57500
|  |  |  | Hardware | Off | TRUE | Testing | Pilot Run | Hardware Engineer 1 | 1 |  |  |  | 95000 | 95000
|  |  |  | Hardware | Off | TRUE | Testing | Durability/Stress | Hardware Engineer 1 | 0.2 |  |  |  | 19000 | 19000
|  |  |  | Hardware | Off | TRUE | Operations | Program Management | Program Manager | 0.5 |  |  |  | 70000 | 70000
|  |  |  | Hardware | Off | TRUE | Operations | Project Management | Project Manager | 2 |  |  |  | 220000 | 220000
|  |  |  | Hardware | Off | TRUE | Operations | Lab Equipment | Equipment Procurement | 150000 |  |  |  | 150000 | 150000
|  |  |  | Hardware | Off | TRUE | Operations | Lab Equipment | Equipment Leasing | 25000 |  |  |  | 25000 | 25000
|  |  |  | pillar | phase | defined | Task | Subtask | Resource | qty | Establish | Evolve | Grow
|  |  |  | Software | On | TRUE | Ideation | Product Experience | Product Manager | 0.75 | 0.75 | 0.795 | 0.9 | 112500 | 112500 | 112500 | 119250 | 135000
|  |  |  | Software | On | TRUE | Ideation | Feasibility | Marketer | 0.3 | 0.3 | 0.318 | 0.36 | 30000 | 30000 | 30000 | 31800 | 36000
|  |  |  | Software | On | TRUE | Ideation | Finance Support | Analyst | 0.2 | 0.2 | 0.212 | 0.24 | 15000 | 15000 | 15000 | 15900 | 18000
|  |  |  | Software | On | TRUE | Ideation | Market Research | Analyst | 0.3 | 0.3 | 0.318 | 0.36 | 22500 | 22500 | 22500 | 23850 | 27000
|  |  |  | Software | On | TRUE | Design | User journey | UX Designer | 0.1 | 0.1 | 0.106 | 0.12 | 11000 | 11000 | 11000 | 11660 | 13200
|  |  |  | Software | On | TRUE | Design | API contract | Software Engineer 2 | 0.2 | 0.2 | 0.212 | 0.24 | 26000 | 26000 | 26000 | 27560 | 31200
|  |  |  | Software | On | TRUE | Design | Data model | Software Engineer 2 | 2 | 2 | 2.12 | 2.4 | 260000 | 260000 | 260000 | 275600 | 312000
|  |  |  | Software | On | TRUE | Prototype | UI Simulation | UX Designer | 0.5 | 0.5 | 0.53 | 0.6 | 55000 | 55000 | 55000 | 58300 | 66000
|  |  |  | Software | On | TRUE | Prototype | Data Model Mockup | Software Engineer 2 | 0.5 | 0.5 | 0.53 | 0.6 | 65000 | 65000 | 65000 | 68900 | 78000
|  |  |  | Software | On | TRUE | Development | Operating Environment | Software Engineer 1 | 0.2 | 0.2 | 0.212 | 0.24 | 21000 | 21000 | 21000 | 22260 | 25200
|  |  |  | Software | On | TRUE | Development | Security Hardening | Software Engineer 1 | 0.2 | 0.2 | 0.212 | 0.24 | 21000 | 21000 | 21000 | 22260 | 25200
|  |  |  | Software | On | TRUE | Development | Unit Testing | Software Engineer 1 | 0.1 | 0.1 | 0.106 | 0.12 | 10500 | 10500 | 10500 | 11130 | 12600
|  |  |  | Software | On | TRUE | Testing | Integration Testing | Software Engineer 2 | 0.3 | 0.3 | 0.318 | 0.36 | 39000 | 39000 | 39000 | 41340 | 46800
|  |  |  | Software | On | TRUE | Testing | Penetration Testing | Software Engineer 1 | 0.8 | 0.8 | 0.848 | 0.96 | 84000 | 84000 | 84000 | 89040 | 100800
|  |  |  | Software | On | TRUE | Testing | UX Workflow Testing | UX Analyst | 0.1 | 0.1 | 0.106 | 0.12 | 9500 | 9500 | 9500 | 10070 | 11400
|  |  |  | Software | On | TRUE | Operations | Program Management | Program Manager | 0.9 | 0.9 | 0.954 | 1.08 | 126000 | 126000 | 126000 | 133560 | 151200
|  |  |  | Software | On | TRUE | Operations | Project Management | Project Manager | 0.5 | 0.5 | 0.53 | 0.6 | 55000 | 55000 | 55000 | 58300 | 66000
|  |  |  | Software | On | TRUE | Operations | Office Equipment | Equipment Leasing | 2500 | 2500 | 2650 | 3000 | 2500 | 2500 | 2500 | 2650 | 3000
[5 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
[5 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
[5 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
[5 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
[5 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
[5 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
[5 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
[5 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
[5 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
[5 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
[5 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A