## Setup
Name | Consumer Electronic
Cost Modeling | Off |  |  | Start | 2024-09-27
Hashing | Off |  |  | Periods | Quarter
Copyright 2024 Paul Galjan
Workstreams |  |  | Phases
Order | Worksheet | Workstream | Include | Phase | Periods | Multiplier | Start | End | hash
1 | Hardware | Hardware | Yes | Phase 1 | 2 | 0% | 2024-09-27 | 2025-03-27
2 | Software | Software | Yes | Phase 2 | 4 | 6% | 2025-03-28 | 2026-03-28
|  |  | Yes | Phase 3 | 8 | 20% | 2026-03-29 | 2028-03-29
|  |  | Yes | Phase 4 | 8 | -5% | 2028-03-30 | 2030-03-30
Formulas:
Start = IF(OR([Periods]="",J8=""),"",IF([Start, row above]="Start",Setup!$H4,[End, row above]+1))
End = IF(OR([Periods]="",K8=""),"",EDATE([Start],([Quarter]*(SWITCH(Setup!H$5,"Year",12,"Quarter",3,"Month",1,"Week",0.25,"Day",12/30)))))
Structure Planner
Permission is hereby granted, free of charge, to any person obtaining a copy of this software and associated documentation files (the “Software”), to deal in the Software without restriction, including without limitation the rights to use, copy, modify, merge, publish, distribute, sublicense, and/or sell copies of the Software, and to permit persons to whom the Software is furnished to do so, subject to the following conditions:
The above copyright notice and this permission notice shall be included in all copies or substantial portions of the Software.
THE SOFTWARE IS PROVIDED “AS IS”, WITHOUT WARRANTY OF
ANY KIND, EXPRESS OR IMPLIED, INCLUDING BUT NOT LIMITED TO THE WARRANTIES OF MERCHANTABILITY, FITNESS FOR A PARTICULAR PURPOSE AND NONINFRINGEMENT. IN NO EVENT SHALL THE AUTHORS OR COPYRIGHT HOLDERS BE LIABLE FOR ANY CLAIM, DAMAGES OR OTHER LIABILITY, WHETHER IN AN ACTION OF CONTRACT, TORT OR OTHERWISE, ARISING FROM, OUT OF OR IN CONNECTION WITH THE SOFTWARE OR THE USE OR OTHER DEALINGS IN THE SOFTWARE.

## Dashboard
Hardware | Software
Hardware | Software
Measures | Measures
6 | 6
21 | 17
19 | 9
14.7 fte | 8.0 fte
Tasks | Tasks
• Ideation 4 subtasks, 4 resources, 1.3 fte | • Ideation 4 subtasks, 3 resources, 1.3 fte
• Design 9 subtasks, 8 resources, 3.1 fte | • Design 3 subtasks, 2 resources, 2.3 fte
• Prototype 3 subtasks, 3 resources, 1.8 fte | • Prototype 2 subtasks, 2 resources, 0.5 fte
• Development 4 subtasks, 4 resources, 2.9 fte | • Development 3 subtasks, 1 resources, 0.3 fte
• Testing 5 subtasks, 3 resources, 1.8 fte | • Testing 3 subtasks, 3 resources, 1.2 fte
• Operations 4 subtasks, 4 resources, 2.9 fte | • Operations 2 subtasks, 2 resources, 1.4 fte
Structure Planner

## Hardware
[6 empty] | workstream | hash | defined | expType | resType | Task | Subtask | Resource | Phase 1 | Phase 2 | Phase 3 | Phase 4 | 1 | Design | Assembly | Analyst
Workstream | Hardware |  |  |  |  | Hardware |  | TRUE | Opex | fte | Ideation | Product Experience | Product Manager | 0.75 | 0.795 | 0.954 | 0.9063 |  | Development | CAD | CAD Designer
[6 empty] | Hardware | 42461DC1 | TRUE | Opex | fte | Ideation | Feasibility | Marketer | 0.3 | 0.318 | 0.3816 | 0.36252 |  | Ideation | CNC/3d print | Contract Analyst
display | Task | subtasks | resources | fte | cost | Hardware | B54CF20C | TRUE | Opex | fte | Ideation | Finance Support | Finance Analyst | 0.2 | 0.212 | 0.2544 | 0.24168 |  | Operations | Day 0 / Packaging | Director
• Ideation 4 subtasks, 4 resources, 1.3 fte | Ideation | 4 | 4 | 1.25 |  | Hardware | 6B66993A | TRUE | Opex | fte | Ideation | Market Research | Market Analyst | 0.3 | 0.318 | 0.3816 | 0.36252 |  | Prototype | Day 1 | Equipment Leasing
• Design 9 subtasks, 8 resources, 3.1 fte | Design | 9 | 8 | 3.1 |  | Hardware | E29B40B8 | TRUE | Opex | fte | Design | Day -1 | Offer Analyst | 0.1 | 0.106 | 0.1272 | 0.12084 |  | Testing | Day -1 | Equipment Procurement
• Prototype 3 subtasks, 3 resources, 1.8 fte | Prototype | 3 | 3 | 1.8 |  | Hardware | 9B2919B7 | TRUE | Opex | fte | Design | Day 0 / Packaging | Logistics Analyst | 0.2 | 0.212 | 0.2544 | 0.24168 |  |  | Day 2 | Facilities Maintenance
• Development 4 subtasks, 4 resources, 2.9 fte | Development | 4 | 4 | 2.9 |  | Hardware | 7945D279 | TRUE | Opex | fte | Design | Day 1 | Software Engineer 2 | 2 | 2.12 | 2.544 | 2.4168 |  |  | Design Review | Finance Analyst
• Testing 5 subtasks, 3 resources, 1.8 fte | Testing | 5 | 3 | 1.8 |  | Hardware | B310A6B4 | TRUE | Opex | fte | Design | Day 1 | UX Designer | 0.5 | 0.53 | 0.636 | 0.6042 |  |  | Durability/Stress | General Capex
• Operations 4 subtasks, 4 resources, 2.9 fte | Operations | 4 | 4 | 2.9 |  | Hardware | 602341FB | FALSE |  |  | Design | Day 2 | undefined resource | 0.5 | 0.53 | 0.636 | 0.6042 |  |  | Factory Flow | General Opex
[6 empty] | Hardware | 7F220891 | TRUE | Opex | fte | Design | CAD | CAD Designer | 0.2 | 0.212 | 0.2544 | 0.24168 |  |  | Feasibility | Hardware Engineer 1
[6 empty] | Hardware | 83F229DE | TRUE | Opex | fte | Design | Day 2 | UX Designer | 0.2 | 0.212 | 0.2544 | 0.24168 |  |  | Finance Support | Hardware Engineer 2
[6 empty] | Hardware | 52F71E8C | TRUE | Opex | fte | Design | Design Review | Hardware Engineer 3 | 0.1 | 0.106 | 0.1272 | 0.12084 |  |  | Integration Testing | Hardware Engineer 3
[6 empty] | Hardware | 6C776E89 | TRUE | Opex | fte | Design | Serviceability Review | Support Engineer 2 | 0.3 | 0.318 | 0.3816 | 0.36252 |  |  | Market Research | Logistics Analyst
[6 empty] | Hardware | 6D05D8CE | TRUE | Opex | fte | Prototype | CNC/3d print | Machinist 1 | 0.8 | 0.848 | 1.0176 | 0.96672 |  |  | Pilot Run | Machinist 1
[6 empty] | Hardware | 951D9E8B | TRUE | Opex | fte | Prototype | Assembly | Hardware Engineer 2 | 0.1 | 0.106 | 0.1272 | 0.12084 |  |  | Product Experience | Manager
[6 empty] | Hardware | 9233A545 | TRUE | Opex | fte | Prototype | Durability/Stress | Hardware Engineer 1 | 0.9 | 0.954 | 1.1448 | 1.0876 |  |  | Program Management | Manager 2
[6 empty] | Hardware | 597B2235 | TRUE | Opex | fte | Development | Factory Flow | Program Manager | 0.5 | 0.53 | 0.636 | 0.6042 |  |  | Project Management | Market Analyst
[6 empty] | Hardware | 6D4E6275 | TRUE | Opex | fte | Development | Project Management | Project Manager | 2 | 2.12 | 2.544 | 2.4168 |  |  | Secret Project | Marketer
[6 empty] | Hardware | 26CCA7F8 | TRUE | Opex | fte | Development | Supply Chain | Logistics Analyst | 0.1 | 0.106 | 0.1272 | 0.12084 |  |  | Serviceability Review | Offer Analyst
[6 empty] | Hardware | 3AA33D3B | TRUE | Opex | fte | Development | Supply Chain | Contract Analyst | 0.3 | 0.318 | 0.3816 | 0.36252 |  |  | Supply Chain | Planner
[6 empty] | Hardware | F58B8F8 | TRUE | Opex | fte | Testing | Pilot Run | Hardware Engineer 2 | 0.1 | 0.106 | 0.1272 | 0.12084 |  |  |  | Product Manager
[6 empty] | Hardware | ECBDE8D3 | TRUE | Opex | fte | Testing | Integration Testing | Software Engineer 2 | 0.5 | 0.53 | 0.636 | 0.6042 |  |  |  | Program Manager
[6 empty] | Hardware | 50A0BA04 | TRUE | Opex | fte | Testing | Integration Testing | Hardware Engineer 2 | 0.5 | 0.53 | 0.636 | 0.6042 |  |  |  | Project Manager
[6 empty] | Hardware | E937E7C9 | TRUE | Opex | fte | Testing | Pilot Run | Hardware Engineer 1 | 1 | 1.06 | 1.272 | 1.2084 |  |  |  | Software Engineer 1
[6 empty] | Hardware | 76511CEE | TRUE | Opex | fte | Testing | Durability/Stress | Hardware Engineer 1 | 0.2 | 0.212 | 0.2544 | 0.24168 |  |  |  | Software Engineer 2
[6 empty] | Hardware | E28A6059 | TRUE | Opex | fte | Operations | Program Management | Program Manager | 0.5 | 0.53 | 0.636 | 0.6042 |  |  |  | Support Engineer 2
[6 empty] | Hardware | A0344E32 | TRUE | Opex | fte | Operations | Project Management | Project Manager | 2 | 2.12 | 2.544 | 2.4168 |  |  |  | Travel
[6 empty] | Hardware | 6D8D3EED | FALSE |  |  | Operations | Secret Project | undefined resource | 0.3 | 0.318 | 0.3816 | 0.36252 |  |  |  | undefined resource
[6 empty] | Hardware | 97F8CEEF | FALSE |  |  | Operations | Secret Project | undefined resource 2 | 0.1 | 0.106 | 0.1272 | 0.12084 |  |  |  | undefined resource 2
UX Analyst
UX Designer
Structure Planner
Structure Planner

## Software
[6 empty] | workstream | hash | defined | expType | resType | Task | Subtask | Resource | Phase 1 | Phase 2 | Phase 3 | Phase 4 | 2 | Design | API contract | Analyst
Workstream | Software |  |  |  | EBB4D379 | Software | E1848F72 | TRUE | Opex | fte | Ideation | Product Experience | Product Manager | 0.75 | 0.795 | 0.954 | 0.9063 |  | Development | Data model | CAD Designer
[6 empty] | Software | 42461DC1 | TRUE | Opex | fte | Ideation | Feasibility | Marketer | 0.3 | 0.318 | 0.3816 | 0.36252 |  | Ideation | Data Model Mockup | Contract Analyst
display | Available Tasks | subtasks | resources | fte | cost | Software | B55DC63A | TRUE | Opex | fte | Ideation | Finance Support | Analyst | 0.2 | 0.212 | 0.2544 | 0.24168 |  | Operations | Feasibility | Director
• Ideation 4 subtasks, 3 resources, 1.3 fte | Ideation | 4 | 3 | 1.25 |  | Software | A2A5A54 | TRUE | Opex | fte | Ideation | Market Research | Analyst | 0.3 | 0.318 | 0.3816 | 0.36252 |  | Prototype | Finance Support | Equipment Leasing
• Design 3 subtasks, 2 resources, 2.3 fte | Design | 3 | 2 | 2.3 |  | Software | 92F4FA9D | TRUE | Opex | fte | Design | User journey | UX Designer | 0.1 | 0.106 | 0.1272 | 0.12084 |  | Testing | Integration Testing | Equipment Procurement
• Prototype 2 subtasks, 2 resources, 0.5 fte | Prototype | 2 | 2 | 0.5 |  | Software | EB3DBCC0 | TRUE | Opex | fte | Design | API contract | Software Engineer 2 | 0.2 | 0.212 | 0.2544 | 0.24168 |  |  | Market Research | Facilities Maintenance
• Development 3 subtasks, 1 resources, 0.3 fte | Development | 3 | 1 | 0.3 |  | Software | 7C9EA323 | TRUE | Opex | fte | Design | Data model | Software Engineer 2 | 2 | 2.12 | 2.544 | 2.4168 |  |  | Operating Environment | Finance Analyst
• Testing 3 subtasks, 3 resources, 1.2 fte | Testing | 3 | 3 | 1.2 |  | Software | 27B0488E | TRUE | Opex | fte | Prototype | UI Simulation | UX Designer | 0.5 | 0.53 | 0.636 | 0.6042 |  |  | Penetration Testing | General Capex
• Operations 2 subtasks, 2 resources, 1.4 fte | Operations | 2 | 2 | 1.4 |  | Software | D78DCD8F | TRUE | Opex | fte | Prototype | Data Model Mockup | Software Engineer 2 | 0.5 | 0.53 | 0.636 | 0.6042 |  |  | Product Experience | General Opex
[6 empty] | Software | 56112046 | TRUE | Opex | fte | Development | Operating Environment | Software Engineer 1 | 0.2 | 0.212 | 0.2544 | 0.24168 |  |  | Program Management | Hardware Engineer 1
[6 empty] | Software | 439D6BCC | TRUE | Opex | fte | Development | Security Hardening | Software Engineer 1 | 0.2 | 0.212 | 0.2544 | 0.24168 |  |  | Project Management | Hardware Engineer 2
[6 empty] | Software | 8B37D270 | TRUE | Opex | fte | Development | Unit Testing | Software Engineer 1 | 0.1 | 0.106 | 0.1272 | 0.12084 |  |  | Security Hardening | Hardware Engineer 3
[6 empty] | Software | 546BE114 | TRUE | Opex | fte | Testing | Integration Testing | Software Engineer 2 | 0.3 | 0.318 | 0.3816 | 0.36252 |  |  | UI Simulation | Logistics Analyst
[6 empty] | Software | 99552A10 | TRUE | Opex | fte | Testing | Penetration Testing | Software Engineer 1 | 0.8 | 0.848 | 1.0176 | 0.96672 |  |  | Unit Testing | Machinist 1
[6 empty] | Software | 861250CF | TRUE | Opex | fte | Testing | UX Workflow Testing | UX Analyst | 0.1 | 0.106 | 0.1272 | 0.12084 |  |  | User journey | Manager
[6 empty] | Software | E142BA7D | TRUE | Opex | fte | Operations | Program Management | Program Manager | 0.9 | 0.954 | 1.1448 | 1.0876 |  |  | UX Workflow Testing | Manager 2
[6 empty] | Software | CE3ABAB1 | TRUE | Opex | fte | Operations | Project Management | Project Manager | 0.5 | 0.53 | 0.636 | 0.6042 |  |  |  | Market Analyst
Marketer
Offer Analyst
Planner
Product Manager
Program Manager
Project Manager
Software Engineer 1
Software Engineer 2
Support Engineer 2
Travel
UX Analyst
UX Designer
Structure Planner
Structure Planner
Structure Planner
Structure Planner
Structure Planner
Structure Planner
Structure Planner
Structure Planner
Structure Planner
Structure Planner

## template
|  | worksheet not integrated |  |  |  | workstream | hash | defined | expType | resType | Task | Subtask | Resource | Phase 1 | Phase 2 | Phase 3 | Phase 4 | #N/A | Design | API contract | Analyst
Workstream | Foo Workstream |  |  |  |  | Foo Workstream |  | TRUE | Opex | fte | Ideation | Product Experience | Product Manager | 0.75 | 0.795 | 0.954 | 0.9063 |  | Development | Data model | CAD Designer
[6 empty] | Foo Workstream | 42461DC1 | TRUE | Opex | fte | Ideation | Feasibility | Marketer | 0.3 | 0.318 | 0.3816 | 0.36252 |  | Ideation | Data Model Mockup | Contract Analyst
display | Available Tasks | subtasks | resources | fte | cost | Foo Workstream | B55DC63A | TRUE | Opex | fte | Ideation | Finance Support | Analyst | 0.2 | 0.212 | 0.2544 | 0.24168 |  | Prototype | Feasibility | Director
• Ideation 4 subtasks, 3 resources, 1.3 fte | Ideation | 4 | 3 | 1.25 |  | Foo Workstream | A2A5A54 | TRUE | Opex | fte | Ideation | Market Research | Analyst | 0.3 | 0.318 | 0.3816 | 0.36252 |  |  | Finance Support | Equipment Leasing
• Design 3 subtasks, 2 resources, 2.3 fte | Design | 3 | 2 | 2.3 |  | Foo Workstream | 92F4FA9D | TRUE | Opex | fte | Design | User journey | UX Designer | 0.1 | 0.106 | 0.1272 | 0.12084 |  |  | Market Research | Equipment Procurement
• Prototype 2 subtasks, 2 resources, 0.5 fte | Prototype | 2 | 2 | 0.5 |  | Foo Workstream | EB3DBCC0 | TRUE | Opex | fte | Design | API contract | Software Engineer 2 | 0.2 | 0.212 | 0.2544 | 0.24168 |  |  | Operating Environment | Facilities Maintenance
• Development 2 subtasks, 1 resources, 0.2 fte | Development | 2 | 1 | 0.2 |  | Foo Workstream | 7C9EA323 | TRUE | Opex | fte | Design | Data model | Software Engineer 2 | 2 | 2.12 | 2.544 | 2.4168 |  |  | Product Experience | Finance Analyst
[6 empty] | Foo Workstream | 27B0488E | TRUE | Opex | fte | Prototype | UI Simulation | UX Designer | 0.5 | 0.53 | 0.636 | 0.6042 |  |  | Security Hardening | General Capex
[6 empty] | Foo Workstream | D78DCD8F | TRUE | Opex | fte | Prototype | Data Model Mockup | Software Engineer 2 | 0.5 | 0.53 | 0.636 | 0.6042 |  |  | UI Simulation | General Opex
[6 empty] | Foo Workstream | 56112046 | TRUE | Opex | fte | Development | Operating Environment | Software Engineer 1 | 0.2 | 0.212 | 0.2544 | 0.24168 |  |  | User journey | Hardware Engineer 1
[6 empty] | Foo Workstream | 439D6BCC | TRUE | Opex | fte | Development | Security Hardening | Software Engineer 1 | 0.2 | 0.212 | 0.2544 | 0.24168 |  |  |  | Hardware Engineer 2
Hardware Engineer 3
Logistics Analyst
Machinist 1
Manager
Manager 2
Market Analyst
Marketer
Offer Analyst
Planner
Product Manager
Program Manager
Project Manager
Software Engineer 1
Software Engineer 2
Support Engineer 2
Travel
UX Analyst
UX Designer
Structure Planner
Structure Planner
Structure Planner
Structure Planner
Structure Planner
Structure Planner
Structure Planner
Structure Planner
Structure Planner
Structure Planner
Structure Planner
Structure Planner
Structure Planner
Structure Planner
Structure Planner
Structure Planner

## Resources
Turn on Cost Modeling in the Workstreams sheet to enable resource definition | [5 empty] | 69090EF1
expendType | resourceType | Resource | YearlyMin | YearlyMax | estPerUnit | hash
Opex | fte | Product Manager | 130000 | 170000 | 1 | C13CCA75
Opex | fte | Marketer | 80000 | 120000 | 1 | FF5EC834
Opex | fte | Finance Analyst | 70000 | 100000 | 1 | A6C03801
Opex | fte | Market Analyst | 70000 | 100000 | 1 | E5828C3D
Opex | fte | Offer Analyst | 70000 | 90000 | 1 | 18C53B11
Opex | fte | Logistics Analyst | 60000 | 90000 | 1 | B5AA5DE8
Opex | fte | Software Engineer 2 | 110000 | 150000 | 1 | 5A638AB1
Opex | fte | UX Designer | 90000 | 130000 | 1 | BDAA32A3
Opex | fte | Hardware Engineer 3 | 130000 | 160000 | 1 | D4BB7B0D
Opex | fte | Support Engineer 2 | 70000 | 100000 | 1 | A7D881F9
Opex | fte | Machinist 1 | 45000 | 65000 | 1 | 71663A4
Opex | fte | Hardware Engineer 2 | 100000 | 130000 | 1 | 1FEC6CEA
Opex | fte | Hardware Engineer 1 | 80000 | 110000 | 1 | E8539243
Opex | fte | Program Manager | 120000 | 160000 | 1 | 42F5489A
Opex | fte | Project Manager | 90000 | 130000 | 1 | A68D71CB
Opex | fte | Contract Analyst | 70000 | 100000 | 1 | 71B72AAF
Opex | fte | Software Engineer 1 | 90000 | 120000 | 1 | C2042BE4
Opex | fte | Planner | 60000 | 90000 | 1 | 4968E70D
Opex | fte | Analyst | 60000 | 90000 | 1 | E7F4565B
Opex | fte | UX Analyst | 80000 | 110000 | 1 | 8B6F7050
Opex | fte | Manager | 90000 | 130000 | 1 | E2CE1A56
Opex | fte | Manager 2 | 110000 | 160000 | 1 | EB5D5CFC
Opex | fte | Director | 150000 | 250000 | 1 | D888D8CB
Opex | fte | CAD Designer | 80000 | 120000 | 1 | E17A5BAE
Capex | misc | General Capex |  |  | 1 | 26439352
Opex | misc | General Opex |  |  | 1 | 1AC5260
Opex | services | Travel |  |  | 1 | CCA51D1E
Opex | services | Facilities Maintenance |  |  | 1 | 56BC5B0C
Capex | capital equipment | Equipment Procurement |  |  | 1 | 58A9551D
Opex | services | Equipment Leasing |  |  | 1 | 3E398457
Structure Planner

## enum (hidden)
Hardware | workstream | hash | defined | expType | resType | Task | Subtask | Resource | Phase 1 | Phase 2 | Phase 3 | Phase 4 | 0 | BaseCost | Phase 1 | Phase 2 | Phase 3 | Phase 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Software | Hardware |  | TRUE | Opex | fte | Ideation | Product Experience | Product Manager | 0.75 | 0.795 | 0.954 | 0.9063 |  | 0.75 | 0.795 | 0.954 | 0.9063
0 | Hardware | 42461DC1 | TRUE | Opex | fte | Ideation | Feasibility | Marketer | 0.3 | 0.318 | 0.3816 | 0.36252 |  | 0.3 | 0.318 | 0.3816 | 0.36252
0 | Hardware | B54CF20C | TRUE | Opex | fte | Ideation | Finance Support | Finance Analyst | 0.2 | 0.212 | 0.2544 | 0.24168 |  | 0.2 | 0.212 | 0.2544 | 0.24168
0 | Hardware | 6B66993A | TRUE | Opex | fte | Ideation | Market Research | Market Analyst | 0.3 | 0.318 | 0.3816 | 0.36252 |  | 0.3 | 0.318 | 0.3816 | 0.36252
0 | Hardware | E29B40B8 | TRUE | Opex | fte | Design | Day -1 | Offer Analyst | 0.1 | 0.106 | 0.1272 | 0.12084 |  | 0.1 | 0.106 | 0.1272 | 0.12084
0 | Hardware | 9B2919B7 | TRUE | Opex | fte | Design | Day 0 / Packaging | Logistics Analyst | 0.2 | 0.212 | 0.2544 | 0.24168 |  | 0.2 | 0.212 | 0.2544 | 0.24168
0 | Hardware | 7945D279 | TRUE | Opex | fte | Design | Day 1 | Software Engineer 2 | 2 | 2.12 | 2.544 | 2.4168 |  | 2 | 2.12 | 2.544 | 2.4168
0 | Hardware | B310A6B4 | TRUE | Opex | fte | Design | Day 1 | UX Designer | 0.5 | 0.53 | 0.636 | 0.6042 |  | 0.5 | 0.53 | 0.636 | 0.6042
0 | Hardware | 602341FB | FALSE |  |  | Design | Day 2 | undefined resource | 0.5 | 0.53 | 0.636 | 0.6042
0 | Hardware | 7F220891 | TRUE | Opex | fte | Design | CAD | CAD Designer | 0.2 | 0.212 | 0.2544 | 0.24168 |  | 0.2 | 0.212 | 0.2544 | 0.24168
0 | Hardware | 83F229DE | TRUE | Opex | fte | Design | Day 2 | UX Designer | 0.2 | 0.212 | 0.2544 | 0.24168 |  | 0.2 | 0.212 | 0.2544 | 0.24168
| Hardware | 52F71E8C | TRUE | Opex | fte | Design | Design Review | Hardware Engineer 3 | 0.1 | 0.106 | 0.1272 | 0.12084 |  | 0.1 | 0.106 | 0.1272 | 0.12084
| Hardware | 6C776E89 | TRUE | Opex | fte | Design | Serviceability Review | Support Engineer 2 | 0.3 | 0.318 | 0.3816 | 0.36252 |  | 0.3 | 0.318 | 0.3816 | 0.36252
| Hardware | 6D05D8CE | TRUE | Opex | fte | Prototype | CNC/3d print | Machinist 1 | 0.8 | 0.848 | 1.0176 | 0.96672 |  | 0.8 | 0.848 | 1.0176 | 0.96672
| Hardware | 951D9E8B | TRUE | Opex | fte | Prototype | Assembly | Hardware Engineer 2 | 0.1 | 0.106 | 0.1272 | 0.12084 |  | 0.1 | 0.106 | 0.1272 | 0.12084
| Hardware | 9233A545 | TRUE | Opex | fte | Prototype | Durability/Stress | Hardware Engineer 1 | 0.9 | 0.954 | 1.1448 | 1.0876 |  | 0.9 | 0.954 | 1.1448 | 1.0876
| Hardware | 597B2235 | TRUE | Opex | fte | Development | Factory Flow | Program Manager | 0.5 | 0.53 | 0.636 | 0.6042 |  | 0.5 | 0.53 | 0.636 | 0.6042
| Hardware | 6D4E6275 | TRUE | Opex | fte | Development | Project Management | Project Manager | 2 | 2.12 | 2.544 | 2.4168 |  | 2 | 2.12 | 2.544 | 2.4168
| Hardware | 26CCA7F8 | TRUE | Opex | fte | Development | Supply Chain | Logistics Analyst | 0.1 | 0.106 | 0.1272 | 0.12084 |  | 0.1 | 0.106 | 0.1272 | 0.12084
| Hardware | 3AA33D3B | TRUE | Opex | fte | Development | Supply Chain | Contract Analyst | 0.3 | 0.318 | 0.3816 | 0.36252 |  | 0.3 | 0.318 | 0.3816 | 0.36252
| Hardware | F58B8F8 | TRUE | Opex | fte | Testing | Pilot Run | Hardware Engineer 2 | 0.1 | 0.106 | 0.1272 | 0.12084 |  | 0.1 | 0.106 | 0.1272 | 0.12084
| Hardware | ECBDE8D3 | TRUE | Opex | fte | Testing | Integration Testing | Software Engineer 2 | 0.5 | 0.53 | 0.636 | 0.6042 |  | 0.5 | 0.53 | 0.636 | 0.6042
| Hardware | 50A0BA04 | TRUE | Opex | fte | Testing | Integration Testing | Hardware Engineer 2 | 0.5 | 0.53 | 0.636 | 0.6042 |  | 0.5 | 0.53 | 0.636 | 0.6042
| Hardware | E937E7C9 | TRUE | Opex | fte | Testing | Pilot Run | Hardware Engineer 1 | 1 | 1.06 | 1.272 | 1.2084 |  | 1 | 1.06 | 1.272 | 1.2084
| Hardware | 76511CEE | TRUE | Opex | fte | Testing | Durability/Stress | Hardware Engineer 1 | 0.2 | 0.212 | 0.2544 | 0.24168 |  | 0.2 | 0.212 | 0.2544 | 0.24168
| Hardware | E28A6059 | TRUE | Opex | fte | Operations | Program Management | Program Manager | 0.5 | 0.53 | 0.636 | 0.6042 |  | 0.5 | 0.53 | 0.636 | 0.6042
| Hardware | A0344E32 | TRUE | Opex | fte | Operations | Project Management | Project Manager | 2 | 2.12 | 2.544 | 2.4168 |  | 2 | 2.12 | 2.544 | 2.4168
| Hardware | 6D8D3EED | FALSE |  |  | Operations | Secret Project | undefined resource | 0.3 | 0.318 | 0.3816 | 0.36252
| Hardware | 97F8CEEF | FALSE |  |  | Operations | Secret Project | undefined resource 2 | 0.1 | 0.106 | 0.1272 | 0.12084
| workstream | hash | defined | expType | resType | Task | Subtask | Resource | Phase 1 | Phase 2 | Phase 3 | Phase 4 | 0
| Software | E1848F72 | TRUE | Opex | fte | Ideation | Product Experience | Product Manager | 0.75 | 0.795 | 0.954 | 0.9063 |  | 0.75 | 0.795 | 0.954 | 0.9063
| Software | 42461DC1 | TRUE | Opex | fte | Ideation | Feasibility | Marketer | 0.3 | 0.318 | 0.3816 | 0.36252 |  | 0.3 | 0.318 | 0.3816 | 0.36252
| Software | B55DC63A | TRUE | Opex | fte | Ideation | Finance Support | Analyst | 0.2 | 0.212 | 0.2544 | 0.24168 |  | 0.2 | 0.212 | 0.2544 | 0.24168
| Software | A2A5A54 | TRUE | Opex | fte | Ideation | Market Research | Analyst | 0.3 | 0.318 | 0.3816 | 0.36252 |  | 0.3 | 0.318 | 0.3816 | 0.36252
| Software | 92F4FA9D | TRUE | Opex | fte | Design | User journey | UX Designer | 0.1 | 0.106 | 0.1272 | 0.12084 |  | 0.1 | 0.106 | 0.1272 | 0.12084
| Software | EB3DBCC0 | TRUE | Opex | fte | Design | API contract | Software Engineer 2 | 0.2 | 0.212 | 0.2544 | 0.24168 |  | 0.2 | 0.212 | 0.2544 | 0.24168
| Software | 7C9EA323 | TRUE | Opex | fte | Design | Data model | Software Engineer 2 | 2 | 2.12 | 2.544 | 2.4168 |  | 2 | 2.12 | 2.544 | 2.4168
| Software | 27B0488E | TRUE | Opex | fte | Prototype | UI Simulation | UX Designer | 0.5 | 0.53 | 0.636 | 0.6042 |  | 0.5 | 0.53 | 0.636 | 0.6042
| Software | D78DCD8F | TRUE | Opex | fte | Prototype | Data Model Mockup | Software Engineer 2 | 0.5 | 0.53 | 0.636 | 0.6042 |  | 0.5 | 0.53 | 0.636 | 0.6042
| Software | 56112046 | TRUE | Opex | fte | Development | Operating Environment | Software Engineer 1 | 0.2 | 0.212 | 0.2544 | 0.24168 |  | 0.2 | 0.212 | 0.2544 | 0.24168
| Software | 439D6BCC | TRUE | Opex | fte | Development | Security Hardening | Software Engineer 1 | 0.2 | 0.212 | 0.2544 | 0.24168 |  | 0.2 | 0.212 | 0.2544 | 0.24168
| Software | 8B37D270 | TRUE | Opex | fte | Development | Unit Testing | Software Engineer 1 | 0.1 | 0.106 | 0.1272 | 0.12084 |  | 0.1 | 0.106 | 0.1272 | 0.12084
| Software | 546BE114 | TRUE | Opex | fte | Testing | Integration Testing | Software Engineer 2 | 0.3 | 0.318 | 0.3816 | 0.36252 |  | 0.3 | 0.318 | 0.3816 | 0.36252
| Software | 99552A10 | TRUE | Opex | fte | Testing | Penetration Testing | Software Engineer 1 | 0.8 | 0.848 | 1.0176 | 0.96672 |  | 0.8 | 0.848 | 1.0176 | 0.96672
| Software | 861250CF | TRUE | Opex | fte | Testing | UX Workflow Testing | UX Analyst | 0.1 | 0.106 | 0.1272 | 0.12084 |  | 0.1 | 0.106 | 0.1272 | 0.12084
| Software | E142BA7D | TRUE | Opex | fte | Operations | Program Management | Program Manager | 0.9 | 0.954 | 1.1448 | 1.0876 |  | 0.9 | 0.954 | 1.1448 | 1.0876
| Software | CE3ABAB1 | TRUE | Opex | fte | Operations | Project Management | Project Manager | 0.5 | 0.53 | 0.636 | 0.6042 |  | 0.5 | 0.53 | 0.636 | 0.6042
|  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
|  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
|  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
|  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
|  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
|  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
|  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
|  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
|  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
|  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A