## Workstreams
[7 empty] | Populate additional columns to allow summarization by attributes like organization, department, or owner. | #NAME?
Name | Converged Product
Start | 2024-09-26
Periods | Quarter
dates | Show |  |  |  | Hardware | Software
[5 empty] | Hardware | Software
Phase | Quarters | Multiplier | Start | End | Measures | Measures
Nascent | 2 | 0% | 2024-09-26 | 2025-03-26 | 6 tasks | 6 tasks
Emergent | 4 | 6% | 2025-03-27 | 2026-03-27 | 20 subtasks | 17 subtasks
Growth | 8 | 20% | 2026-03-28 | 2028-03-28 | 18 resources | 9 resources
Mature | 8 | -5% | 2028-03-29 | 2030-03-29 | 18.0 fte | 9.8 fte
[5 empty] | 1222.5 | 637.7
[5 empty] | Tasks | Tasks
[5 empty] | • Ideation 5 subtasks, 5 resources, 4.55 qty | • Ideation 4 subtasks, 3 resources, 1.55 qty
[5 empty] | • Design 8 subtasks, 6 resources, 3.9 qty | • Design 3 subtasks, 3 resources, 2.3 qty
[5 empty] | • Prototype 3 subtasks, 3 resources, 1.8 qty | • Prototype 2 subtasks, 2 resources, 1 qty
[5 empty] | • Development 4 subtasks, 4 resources, 2.9 qty | • Development 3 subtasks, 1 resources, 0.6 qty
[5 empty] | • Testing 5 subtasks, 3 resources, 2.3 qty | • Testing 3 subtasks, 3 resources, 1.8 qty
[5 empty] | • Operations 2 subtasks, 2 resources, 2.5 qty | • Operations 2 subtasks, 2 resources, 2.5 qty
Structure Planner

## Costs
Resource | Yearly
Analyst | 56
Contract Analyst | 65
Finance Analyst | 72
HW Engr 1 | 62
HW Engr 2 | 78
HW Engr 3 | 92
Logistics Analyst | 45
Machinist 1 | 59
Market Analyst | 52
Marketer | 53
Offer Analyst | 42
PDM | 78
PGM 1 | 50
PJM2 | 48
Planner 3 | 96
Support Engr 2 | 42
SW Engr 1 | 66
SW Engr 2 | 82
UX Analyst | 45
UX Designer | 73

## Hardware
[5 empty] | pillar | phase | Task | Subtask | Resource | #REF! |  |  |  |  | Design | Assembly | Contract Analyst
Workstream | Hardware |  | Phased | On | Hardware | On | Ideation | Product Experience | PDM | 0.75 | 0.75 | 0.75 | 0.75 | 0.75 | Development | CNC/3d print | Finance Analyst
[5 empty] | Hardware | On | Ideation | Feasibility | Marketer | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | Ideation | Day 0 / Packaging | HW Engr 1
display | Task | subtasks | resources | qty | Hardware | On | Ideation | Finance Support | Finance Analyst | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | Operations | Day 1 | HW Engr 2
• Ideation 5 subtasks, 5 resources, 4.55 qty | Ideation | 5 | 5 | 4.55 | Hardware | On | Ideation | Market Research | Market Analyst | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | Prototype | Day -1 | HW Engr 3
• Design 8 subtasks, 6 resources, 3.9 qty | Design | 8 | 6 | 3.9 | Hardware | On | Design | Day -1 | Offer Analyst | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | Testing | Day 2 | Logistics Analyst
• Prototype 3 subtasks, 3 resources, 1.8 qty | Prototype | 3 | 3 | 1.8 | Hardware | On | Design | Day 0 / Packaging | Logistics Analyst | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 |  | Design Review | Machinist 1
• Development 4 subtasks, 4 resources, 2.9 qty | Development | 4 | 4 | 2.9 | Hardware | On | Design | Day 1 | SW Engr 2 | 2 | 2 | 2 | 2 | 2 |  | Durability/Stress | Market Analyst
• Testing 5 subtasks, 3 resources, 2.3 qty | Testing | 5 | 3 | 2.3 | Hardware | On | Design | Day 1 | UX Designer | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 |  | Factory Flow | Marketer
• Operations 2 subtasks, 2 resources, 2.5 qty | Operations | 2 | 2 | 2.5 | Hardware | On | Design | Day 2 | SW Engr 2 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 |  | Feasibility | Offer Analyst
[5 empty] | Hardware | On | Design | Day 2 | UX Designer | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 |  | Finance Support | PDM
[5 empty] | Hardware | On | Design | Design Review | HW Engr 3 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 |  | Integration Testing | PGM 1
[5 empty] | Hardware | On | Design | Serviceability Review | Support Engr 2 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 |  | Market Research | PJM2
[5 empty] | Hardware | On | Prototype | CNC/3d print | Machinist 1 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 |  | Pilot Run | Planner 3
[5 empty] | Hardware | On | Prototype | Assembly | HW Engr 2 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 |  | Product Experience | Support Engr 2
[5 empty] | Hardware | On | Prototype | Durability/Stress | HW Engr 1 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 |  | Program Management | SW Engr 1
[5 empty] | Hardware | On | Development | Factory Flow | PGM 1 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 |  | Program Planning | SW Engr 2
[5 empty] | Hardware | On | Development | Project Management | PJM2 | 2 | 2 | 2 | 2 | 2 |  | Project Management | UX Designer
[5 empty] | Hardware | On | Development | Supply Chain | Logistics Analyst | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 |  | Serviceability Review
[5 empty] | Hardware | On | Development | Supply Chain | Contract Analyst | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 |  | Supply Chain
[5 empty] | Hardware | On | Testing | Pilot Run | HW Engr 2 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1
[5 empty] | Hardware | On | Testing | Integration Testing | SW Engr 1 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
[5 empty] | Hardware | On | Testing | Integration Testing | HW Engr 1 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
[5 empty] | Hardware | On | Testing | Pilot Run | HW Engr 2 | 1 | 1 | 1 | 1 | 1
[5 empty] | Hardware | On | Testing | Durability/Stress | HW Engr 1 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2
[5 empty] | Hardware | On | Operations | Program Management | PGM 1 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
[5 empty] | Hardware | On | Operations | Project Management | PJM2 | 2 | 2 | 2 | 2 | 2
[5 empty] | Hardware | On | Ideation | Program Planning | Planner 3 | 3 | 3 | 3 | 3 | 3
Structure Planner
Create Tasks and align them to Subtasks and Resources.
Structure Planner

## Software
[5 empty] | pillar | phase | Task | Subtask | Resource | qty | Design | API contract | Analyst
Workstream | Software |  | Phased | Off | Software | Off | Ideation | Product Experience | PDM | 0.75 | Development | Data model | Marketer
[5 empty] | Software | Off | Ideation | Feasibility | Marketer | 0.3 | Ideation | Data Model Mockup | PDM
display | Available Tasks | subtasks | resources | qty | Software | Off | Ideation | Finance Support | Analyst | 0.2 | Operations | Feasibility | PGM 1
• Ideation 4 subtasks, 3 resources, 1.55 qty | Ideation | 4 | 3 | 1.55 | Software | Off | Ideation | Market Research | Analyst | 0.3 | Prototype | Finance Support | PJM2
• Design 3 subtasks, 3 resources, 2.3 qty | Design | 3 | 3 | 2.3 | Software | Off | Design | User journey | UX Designer | 0.1 | Testing | Integration Testing | SW Engr 1
• Prototype 2 subtasks, 2 resources, 1 qty | Prototype | 2 | 2 | 1 | Software | Off | Design | API contract | SW Engr 1 | 0.2 |  | Market Research | SW Engr 2
• Development 3 subtasks, 1 resources, 0.6 qty | Development | 3 | 1 | 0.6 | Software | Off | Design | Data model | SW Engr 2 | 2 |  | Operating Environment | UX Analyst
• Testing 3 subtasks, 3 resources, 1.8 qty | Testing | 3 | 3 | 1.8 | Software | Off | Prototype | UI Simulation | UX Designer | 0.5 |  | Penetration Testing | UX Designer
• Operations 2 subtasks, 2 resources, 2.5 qty | Operations | 2 | 2 | 2.5 | Software | Off | Prototype | Data Model Mockup | SW Engr 2 | 0.5 |  | Product Experience
[5 empty] | Software | Off | Development | Operating Environment | SW Engr 1 | 0.2 |  | Program Management
[5 empty] | Software | Off | Development | Security Hardening | SW Engr 1 | 0.1 |  | Project Management
[5 empty] | Software | Off | Development | Unit Testing | SW Engr 1 | 0.3 |  | Security Hardening
[5 empty] | Software | Off | Testing | Integration Testing | SW Engr 2 | 0.8 |  | UI Simulation
[5 empty] | Software | Off | Testing | Penetration Testing | SW Engr 1 | 0.1 |  | Unit Testing
[5 empty] | Software | Off | Testing | UX Workflow Testing | UX Analyst | 0.9 |  | User journey
[5 empty] | Software | Off | Operations | Program Management | PGM 1 | 0.5 |  | UX Workflow Testing
[5 empty] | Software | Off | Operations | Project Management | PJM2 | 2
Structure Planner
Structure Planner
Create Tasks and align them to Subtasks and Resources.
Structure Planner
Structure Planner
Structure Planner
Structure Planner

## enum
Worksheet | Workstream | Tasks | pillar | phase | Task | Subtask | Resource | #REF! | 0 | 0 | 0 | 0 | BaseCost | Nascent | Emergent | Growth | Mature
Hardware | Hardware | 6 | Hardware | On | Ideation | Product Experience | PDM | 0.75 | 0.75 | 0.75 | 0.75 | 0.75 | 58.5
Software | Software | 6 | Hardware | On | Ideation | Feasibility | Marketer | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 15.9
|  |  | Hardware | On | Ideation | Finance Support | Finance Analyst | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 14.4
|  |  | Hardware | On | Ideation | Market Research | Market Analyst | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 15.6
|  |  | Hardware | On | Design | Day -1 | Offer Analyst | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 4.2
|  |  | Hardware | On | Design | Day 0 / Packaging | Logistics Analyst | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 9
|  |  | Hardware | On | Design | Day 1 | SW Engr 2 | 2 | 2 | 2 | 2 | 2 | 164
|  |  | Hardware | On | Design | Day 1 | UX Designer | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 36.5
|  |  | Hardware | On | Design | Day 2 | SW Engr 2 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 41
|  |  | Hardware | On | Design | Day 2 | UX Designer | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 14.6
|  |  | Hardware | On | Design | Design Review | HW Engr 3 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 9.2
|  |  | Hardware | On | Design | Serviceability Review | Support Engr 2 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 12.6
|  |  | Hardware | On | Prototype | CNC/3d print | Machinist 1 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 47.2
|  |  | Hardware | On | Prototype | Assembly | HW Engr 2 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 7.8
|  |  | Hardware | On | Prototype | Durability/Stress | HW Engr 1 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 55.8
|  |  | Hardware | On | Development | Factory Flow | PGM 1 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 25
|  |  | Hardware | On | Development | Project Management | PJM2 | 2 | 2 | 2 | 2 | 2 | 96
|  |  | Hardware | On | Development | Supply Chain | Logistics Analyst | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 4.5
|  |  | Hardware | On | Development | Supply Chain | Contract Analyst | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 19.5
|  |  | Hardware | On | Testing | Pilot Run | HW Engr 2 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 7.8
|  |  | Hardware | On | Testing | Integration Testing | SW Engr 1 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 33
|  |  | Hardware | On | Testing | Integration Testing | HW Engr 1 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 31
|  |  | Hardware | On | Testing | Pilot Run | HW Engr 2 | 1 | 1 | 1 | 1 | 1 | 78
|  |  | Hardware | On | Testing | Durability/Stress | HW Engr 1 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 12.4
|  |  | Hardware | On | Operations | Program Management | PGM 1 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 25
|  |  | Hardware | On | Operations | Project Management | PJM2 | 2 | 2 | 2 | 2 | 2 | 96
|  |  | Hardware | On | Ideation | Program Planning | Planner 3 | 3 | 3 | 3 | 3 | 3 | 288
|  |  | pillar | phase | Task | Subtask | Resource | qty | 0 | 0 | 0 | 0
|  |  | Software | Off | Ideation | Product Experience | PDM | 0.75 |  |  |  |  | 58.5
|  |  | Software | Off | Ideation | Feasibility | Marketer | 0.3 |  |  |  |  | 15.9
|  |  | Software | Off | Ideation | Finance Support | Analyst | 0.2 |  |  |  |  | 11.2
|  |  | Software | Off | Ideation | Market Research | Analyst | 0.3 |  |  |  |  | 16.8
|  |  | Software | Off | Design | User journey | UX Designer | 0.1 |  |  |  |  | 7.3
|  |  | Software | Off | Design | API contract | SW Engr 1 | 0.2 |  |  |  |  | 13.2
|  |  | Software | Off | Design | Data model | SW Engr 2 | 2 |  |  |  |  | 164
|  |  | Software | Off | Prototype | UI Simulation | UX Designer | 0.5 |  |  |  |  | 36.5
|  |  | Software | Off | Prototype | Data Model Mockup | SW Engr 2 | 0.5 |  |  |  |  | 41
|  |  | Software | Off | Development | Operating Environment | SW Engr 1 | 0.2 |  |  |  |  | 13.2
|  |  | Software | Off | Development | Security Hardening | SW Engr 1 | 0.1 |  |  |  |  | 6.6
|  |  | Software | Off | Development | Unit Testing | SW Engr 1 | 0.3 |  |  |  |  | 19.8
|  |  | Software | Off | Testing | Integration Testing | SW Engr 2 | 0.8 |  |  |  |  | 65.6
|  |  | Software | Off | Testing | Penetration Testing | SW Engr 1 | 0.1 |  |  |  |  | 6.6
|  |  | Software | Off | Testing | UX Workflow Testing | UX Analyst | 0.9 |  |  |  |  | 40.5
|  |  | Software | Off | Operations | Program Management | PGM 1 | 0.5 |  |  |  |  | 25
|  |  | Software | Off | Operations | Project Management | PJM2 | 2 |  |  |  |  | 96
[5 empty] | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0